## Project Plan Summary
PSP3 Project Plan Summary - Program
Student | Jesús Alberto Goiz Barrales |  |  | Date | 2017-03-15
Program | Alta-Alumnos |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Summary
LOC/Hour |  | 22.15 | 50.16 | 31.06
Planned Time |  | 703 |  | 1206
Actual Time |  |  | 263 | 1531
CPI (Planned/Actual Time) |  |  |  | 0.79
% Reused |  | 2.4 | 0 | 28.9
% New Reused |  | 0 | 3.2 | 1.5
Test Defects/KLOC |  | 7.81 | 32.26 | 19.03
Total Defects/KLOC |  | 148.44 | 82.95 | 118.39
Yield % |  | 81.6 | 75.3 | 55.4
% Appraisal COQ |  | 21.2 | 27 | 22.9
% Failure COQ |  | 10.3 | 40.7 | 19.1
COQ A/F Ratio |  | 2.05 | 0.66 | 1.2
Program Size (LOC)
Base(B) |  | 0 | 0
Deleted(D) |  | 0 | 0
Modified(M) |  | 0 | 0
Added(A) |  | 118 | 220
Reused(R) |  | 0 | 0 | 270
Total N&C (N) |  | 118 | 220 | 476
Total LOC(T) |  | 118 | 220 | 937
Total New Reused |  | 0 | 7 | 7
Total Object LOC(E) |  | 175.79 | 152 | 446
UPI (70%) |  | 152
LPI (70%) |  | 85
Time in Phase (min.)
Planning |  | 15 | 15 | 192 | 21
High-level Design |  | 5 | 0 | 0 | 0
HLDR |  | 5 | 0 | 0 | 0
Design |  | 45 | 31 | 162 | 17.8
Design Review |  | 10 | 58 | 131 | 14.4
Code |  | 20 | 19 | 104 | 11.3
Code Review |  | 10 | 13 | 78 | 8.5
Compile |  | 2 | 77 | 92 | 10
Test |  | 5 | 30 | 82 | 9
Postmortem |  | 5 | 20 | 72 | 7.9
Total |  | 122 | 263 | 913 | 99.9
UPI (70%) |  | 501
LPI (70%) |  | 193
PSP3 Project Plan Summary - Program N/A (Continued)
Student | Jesús Alberto Goiz Barrales |  |  | Date | 2017-03-15
Program | Alta-Alumnos |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Defects Injected
Planning |  | 0 | 0 | 0 | 0
High-level Design |  | 0 | 0 | 0 | 0
HLDR |  | 0 | 0 | 0 | 0
Design |  | 2.3 | 8 | 13 | 18.8
Design Review |  | 0.9 | 0 | 2 | 2.9
Code |  | 14.3 | 23 | 54 | 78.3
Code Review |  | 0 | 0 | 0 | 0
Compile |  | 0 | 0 | 0 | 0
Test |  | 0 | 0 | 0 | 0
Total Development |  | 17.5 | 31 | 69 | 100
Defects Removed
Planning |  | 0 | 0 | 0 | 0
High-level Design |  | 0 | 0 | 0 | 0
HLDR |  | 0 | 0 | 0 | 0
Design |  | 0 | 0 | 0 | 0
Design Review |  | 4.3 | 8 | 15 | 21.7
Code |  | 0 | 0 | 0 | 0
Code Review |  | 14.8 | 4 | 28 | 40.6
Compile |  | 3.1 | 11 | 16 | 23.2
Test |  | 1.2 | 8 | 10 | 14.5
Total Development |  | 23.4 | 31 | 69 | 100
After Development |  |  | ????? | ?????
Defect Removal Efficiency
Def/Hr - HLDR |  | 0 | 0 | 0
Def/Hr - DLDR |  | 5.6 | 8.28 | 6.85
Def/Hr - CDR |  | 21.85 | 18.46 | 21.67
Def/Hr - Compile |  | 19.91 | 8.57 | 10.46
Def/Hr - Test |  | 2.24 | 16 | 7.28
DRL(HLDR/UT) |  | 0 | 0 | 0
DRL(DLDR/UT) |  | 2.5 | 0.52 | 0.94
DRL(CDR/UT) |  | 9.76 | 1.15 | 2.98
DRL(Compile/UT) |  | 8.89 | 0.54 | 1.44

## Size estimated template
Size Estimating Template
Student | Jesús Alberto Goiz Barrales |  |  |  | Date |  | 2017-03-20
Instructor | PEBM |  |  |  | Program# |  | N/A
BASE PROGRAM LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE SIZE (B) => |  |  |  |  | 0 |  | 110
LOC DELETED (D) => |  |  |  |  | 0 |  | 80
LOC MODIFIED (M) => |  |  |  |  | 0 |  | 10
OBJECT LOC
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC |  | C++ Object Size in LOC per Method
[9 empty] | Category | VS | S | M | L | VL
[9 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[9 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[9 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[9 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
(BA) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
TOTAL BASE ADDITIONS (BA) |  |  |  |  | 0 |  | 0 |  | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
Alta_Alumno |  | I/O | 1 | L | 22 |  | 39
Insert_Alumno |  | Set-up | 1 | VL | 12 |  | 41
Qery_Alumno |  | TEXT | 1 | L | 36 |  | 32
callback |  | TEXT | 1 | L | 36 |  | 10
print_archivo |  | I/O | 1 | L | 22 |  | 10
void actualizar |  | LOGIC | 1 | L | 36 |  | 20
(NO) subtotal from page 2 |  |  |  |  | 0 |  | 0
TOTAL NEW OBJECTS (NO) |  |  |  |  | 164 |  | 152
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
(R) subtotal from page 2 |  |  |  |  | 0 |  | 0
REUSED TOTAL (R) |  |  |  |  | 0 |  | 0
[5 empty] | Size |  | Time
Estimated Object LOC: |  |  | E = BA+NO+M |  | 164
Regression Parameter: |  |  | B0 |  | 0 |  | 0
Regression Parameter: |  |  | B1 |  | 1.2 |  | 2.26
Estimated New and Changed LOC: |  |  | N = B0 + B1` * E |  | 196.8
Estimated Total LOC: |  |  | T = N + B - D - M + R |  | 196.8
Estimated Total New Reuse (sum of * LOC): |  |  |  |  | 0
Estimated Total Developent Time: |  |  | Time = B0 + B1` * E |  |  |  | 81
Prediction Range: |  |  | Range |  | 0 |  | 0
Upper Prediction Interval: |  |  | UPI = N + Range |  | 0 |  | 0
Lower Prediction Interval: |  |  | LPI = N - Range |  | 0 |  | 0
Prediction Interval Percent |  |  |  |  | 70% |  | 70%
Method Selected |  |  |  |  | C |  | C
R^2 |  |  |  |  | 0 |  | 0
Size Estimating Template (continued)
Student | Jesús Alberto Goiz Barrales |  |  |  | Date |  | 2017-03-20
Instructor | PEBM |  |  |  | Program# |  | N/A
OBJECT LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC
C++ Object Size in LOC per Method
[15 empty] | Category | VS | S | M | L | VL
[15 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[15 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[15 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[15 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
[15 empty] | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
[15 empty] | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
SUBTOTAL BASE ADDITIONS (BA) => |  |  |  |  | 0 |  | 0
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
SUBTOTAL NEW OBJECTS (NO) => |  |  |  |  | 0 |  | 0
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
SUBTOTAL REUSED (R) => |  |  |  |  | 0 |  | 0

## Task Planning Template
| Project | Alta-Alumnos |  |  |  | Instructor | PEBM
Task |  | Plan |  |  |  |  | Actual
Number | Name | Minutes | Planned Value | Cumulative Minutes | Cumulative Planned Value | Date Monday | Date | Earned Value | Cumulative Earned Value
1 | Planning | 15 | 12.3% | 15 | 12.3% | 2017-03-10 | 2017-03-26 | 12.3% | 12.3%
2 | High-level Design | 5 | 4.098% | 20 | 16.39% | 2017-03-15 | 2017-03-26 | 4.098% | 16.39%
3 | HLDR | 5 | 4.098% | 25 | 20.49% | 2017-03-15 | 2017-03-26 | 4.098% | 20.49%
4 | Design | 45 | 36.89% | 70 | 57.38% | 2017-03-15 | 2017-03-15 | 36.89% | 57.38%
5 | Design Review | 10 | 8.197% | 80 | 65.57% | 2017-03-15 | 2017-03-15 | 8.197% | 65.57%
6 | Code | 20 | 16.39% | 100 | 81.97% | 2017-03-16 | 2017-03-15 | 16.39% | 81.97%
7 | Code Review | 10 | 8.197% | 110 | 90.16% | 2017-04-03 | 2017-03-16 | 8.197% | 90.16%
8 | Compile | 2 | 1.639% | 112 | 91.8% | 2017-04-04 | 2017-04-03 | 1.639% | 91.8%
9 | Test | 5 | 4.098% | 117 | 95.9% | 2017-04-05 | 2017-04-04 | 4.098% | 95.9%
10 | Postmortem | 5 | 4.098% | 122 | 100% | 2017-04-05 | 2017-04-05 | 4.098% | 100%
| Total | 122 | 100%
Formulas:
Actual = [Date Monday, row above]

## Schedule Planning Template
Table C49 Schedule Planning Template
| Student | Jesús Alberto Goiz Barrales |  |  |  | Date | 2017-03-15
| Project | Alta-Alumnos |  |  |  | Instructor | PEBM
|  | Plan |  |  | Actual
Day Number | Date Monday | Direct Min | Cumutative Minute | Cumulative Planned Value | Direct Min | Cumulative Minutes | Cumulative Earned Value
4 | 2017-03-20 | 15 | 15 | 12.3% | 15 | 15 | 12.3%
4 | 2017-03-20 | 5 | 20 | 16.39% | 0 | 15 | 16.39%
4 | 2017-03-20 | 5 | 25 | 20.49% | 0 | 15 | 20.49%
4 | 2017-03-20 | 45 | 70 | 57.38% | 31 | 46 | 57.38%
4 | 2017-03-20 | 10 | 80 | 65.57% | 58 | 104 | 65.57%
7 | 2017-03-23 | 20 | 100 | 81.97% | 19 | 123 | 81.97%
7 | 2017-03-23 | 10 | 110 | 90.16% | 13 | 136 | 90.16%
3 | 2017-04-03 | 2 | 112 | 91.8% | 77 | 213 | 91.8%
3 | 2017-04-04 | 5 | 117 | 95.9% | 30 | 243 | 95.9%
3 | 2017-04-05 | 5 | 122 | 100% | 20 | 263 | 100%