## Summary
PSP3 Project Plan Summary - Program 10A
Student | 24400093-Guillermo Vivaldo Vazquez |  |  | Date | 15/03/17
Program | Alta De Planes |  |  | Program#
Instructor | Patricia Erendira Benavides Muratalla |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Summary
LOC/Hour |  | 35.4 | 30.46 | 39.06
Planned Time |  | 99 |  | 1065
Actual Time |  |  | 618 | 1725
CPI (Planned/Actual Time) |  |  |  | 0.62
% Reused |  | 0 | 0 | 4.5
% New Reused |  | 0 | 0 | 0
Test Defects/KLOC |  | 0 | 6.37 | 2.97
Total Defects/KLOC |  | 22.28 | 31.85 | 26.75
Yield % |  | 87.5 | 70 | 77.8
% Appraisal COQ |  | 11.8 | 5.4 | 8
% Failure COQ |  | 6.5 | 7.7 | 7.2
COQ A/F Ratio |  | 1.82 | 0.71 | 1.11
Program Size (LOC)
Base(B) |  | 0 | 0
Deleted(D) |  | 0 | 0
Modified(M) |  | 0 | 0
Added(A) |  | 58 | 314
Reused(R) |  | 0 | 0 | 46
Total N&C (N) |  | 58 | 314 | 673
Total LOC(T) |  | 58 | 314 | 1031
Total New Reused |  | 0 | 0 | 0
Total Object LOC(E) |  | 48.6 | 307 | 653
UPI (70%)
LPI (70%)
Time in Phase (min.)
Planning |  | 27 | 56 | 169 | 16.3
High-level Design |  | 0 | 0 | 0 | 0
HLDR |  | 0 | 0 | 0 | 0
Design |  | 23 | 276 | 373 | 36.1
Design Review |  | 5 | 27 | 49 | 4.7
Code |  | 27 | 205 | 319 | 30.9
Code Review |  | 6 | 7 | 34 | 3.3
Compile |  | 0 | 20 | 22 | 2.1
Test |  | 6 | 28 | 53 | 5.1
Postmortem |  | 4 | 0 | 16 | 1.5
Total |  | 99 | 618 | 1034 | 100
UPI (70%) |  | 137
LPI (70%) |  | 60
PSP3 Project Plan Summary - Program 10A (Continued)
Student | 24400093-Guillermo Vivaldo Vazquez |  |  | Date | ?????
Program | Alta De Planes |  |  | Program# | 10A
Instructor | Patricia Erendira Benavides Muratalla |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Defects Injected
Planning |  | 0 | 0 | 0 | 0
High-level Design |  | 0 | 0 | 0 | 0
HLDR |  | 0 | 0 | 0 | 0
Design |  | 0.2 | 4 | 5 | 27.8
Design Review |  | 0 | 0 | 0 | 0
Code |  | 1.1 | 6 | 13 | 72.2
Code Review |  | 0 | 0 | 0 | 0
Compile |  | 0 | 0 | 0 | 0
Test |  | 0 | 0 | 0 | 0
Total Development |  | 1.3 | 10 | 18 | 100
Defects Removed
Planning |  | 0 | 0 | 0 | 0
High-level Design |  | 0 | 0 | 0 | 0
HLDR |  | 0 | 0 | 0 | 0
Design |  | 0 | 0 | 0 | 0
Design Review |  | 0.2 | 4 | 5 | 27.8
Code |  | 0 | 0 | 0 | 0
Code Review |  | 1 | 3 | 9 | 50
Compile |  | 0.2 | 1 | 2 | 11.1
Test |  | 0 | 2 | 2 | 11.1
Total Development |  | 1.3 | 10 | 18 | 100
After Development |  |  | 0 | 0
Defect Removal Efficiency
Def/Hr - HLDR |  | 0 | 0 | 0
Def/Hr - DLDR |  | 1.9 | 8.88 | 6.18
Def/Hr - CDR |  | 9 | 27 | 15.91
Def/Hr - Compile |  | 21.94 | 2.99 | 5.48
Def/Hr - Test |  | 0 | 4.33 | 2.28
DRL(HLDR/UT) |  | 0 | 0 | 0
DRL(DLDR/UT) |  | 0 | 2.05 | 2.71
DRL(CDR/UT) |  | 0 | 6.23 | 6.98
DRL(Compile/UT) |  | 0 | 0.69 | 2.4

## Size Estimating Template
Size Estimating Template
Student | Guillermo Vivaldo Vazquez | 24400093-Guillermo Vivaldo Vazquez |  |  | Date | 15/03/17
Instructor | Jorge Rafael Aguilar Cisneros | Patricia Erendira Benavides Muratalla |  |  | Program# | 10A
BASE PROGRAM LOC |  |  |  |  | ESTIMATE | ACTUAL
BASE SIZE (B) => |  |  |  |  | 0 | 0
LOC DELETED (D) => |  |  |  |  | 0 | 0
LOC MODIFIED (M) => |  |  |  |  | 0 | 0
OBJECT LOC
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC | LOC
C++ Object Size in LOC per Method
[8 empty] | Category | VS | S | M | L | VL
[8 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[8 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[8 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
(BA) subtotal from page 2 |  |  |  |  | 0 | 0 |  | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
TOTAL BASE ADDITIONS (BA) |  |  |  |  | 0 | 0 |  | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | LOC |  | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
struct_plan |  | Logic | 1 | S | 10.98 | 0
alta_plan |  | I/O | 1 | S | 12.06 | 112
alta_semestre |  | I/O | 1 | VS | 9.01 | 0
asignacion_materia |  | I/O | 1 | VS | 9 | 0
int_main |  | Logic | 1 | VS | 7.55 | 9
static int callback |  | I/O | 1 | VS |  | 11
query_planes |  | I/O | 1 | VL |  | 47
insert_mtr_plan |  | I/O | 1 | L |  | 27
(NO) subtotal from page 2 |  |  |  |  | 0 | 101
TOTAL NEW OBJECTS (NO) |  |  |  |  | 48.6 | 307
REUSED OBJECTS |  |  |  |  | LOC | LOC
(R) subtotal from page 2 |  |  |  |  | 0 | 0
REUSED TOTAL (R) |  |  |  |  | 0 | 0
[5 empty] | Size | Time
Estimated Object LOC: |  |  | E = BA+NO+M |  | 48.6
Regression Parameter: |  |  | B0 |  | 0 | 59.3899
Regression Parameter: |  |  | B1 |  | 1.1961 | 0.80528
Estimated New and Changed LOC: |  |  | N = B0 + B1` * E |  | 58.1297
Estimated Total LOC: |  |  | T = N + B - D - M + R |  | 58.1297
Estimated Total New Reuse (sum of * LOC): |  |  |  |  | 0
Estimated Total Developent Time: |  |  | Time = B0 + B1` * E |  |  | 98.5264
Prediction Range: |  |  | Range |  | 0 | 38.6482
Upper Prediction Interval: |  |  | UPI = N + Range |  |  | 137.1747
Lower Prediction Interval: |  |  | LPI = N - Range |  |  | 59.8782
Prediction Interval Percent |  |  |  |  | 70% | 70%
Method Selected |  |  |  |  | C | A
R^2 |  |  |  |  | 0 | 0.56041
Size Estimating Template (continued)
Student | Guillermo Vivaldo Vazquez |  |  |  | Date | ?????
Instructor | Jorge Rafael Aguilar Cisneros |  |  |  | Program# | 10A
OBJECT LOC |  |  |  |  | ESTIMATE | ACTUAL
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC | LOC
insert_materias |  | I/O | 1 | L |  | 24 |  | C++ Object Size in LOC per Method
insert_planes |  | I/O | 1 | VL |  | 30 |  | Category | VS | S | M | L | VL
static int print_archivo |  | Logic | 1 | S |  | 10 |  | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
alta_materias |  | I/O | 1 | VL |  | 37 |  | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[8 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[8 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
[8 empty] | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
[8 empty] | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
*
SUBTOTAL NEW OBJECTS (NO) => |  |  |  |  | 0 | 101
SUBTOTAL NEW OBJECTS (NO) => |  |  |  |  | 0 | 0
REUSED OBJECTS |  |  |  |  | LOC | LOC
SUBTOTAL REUSED (R) => |  |  |  |  | 0 | 0

## TaskPlanning
| Project | Menu-principal |  |  |  | Instructor | PEBM
Task |  | Plan |  |  |  |  | Actual
Number | Name | Minutes | Planned Value | Cumulative Minutes | Cumulative Planned Value | Date Monday | Date | Earned Value | Cumulative Earned Value
1 | Planning | 27 | 20% | 27 | 20% | 2017-03-15 | 2017-03-15 | 20% | 20%
2 | High-level Design | 0 | 0% | 27 | 20% | 2017-03-15 | 2017-03-15 | 0% | 20%
3 | HLDR | 0 | 0% | 27 | 20% | 2017-03-15 | 2017-03-15 | 0% | 20%
4 | Design | 23 | 46% | 50 | 66% | 2017-03-15 | 2017-03-20 | 46% | 66%
5 | Design Review | 5 | 6% | 55 | 72% | 2017-03-15 | 2017-03-22 | 6% | 72%
6 | Code | 27 | 14% | 82 | 86% | 2017-03-17 | 2017-03-29 | 14% | 86%
7 | Code Review | 6 | 6% | 88 | 92% | 2017-03-17 | 2017-03-30 | 6% | 92%
8 | Compile | 0 | 1% | 88 | 93% | 2017-03-18 | 2017-03-30 | 1% | 93%
9 | Test | 6 | 5% | 94 | 98% | 2017-03-18 | 2017-04-03 | 5% | 98%
10 | Postmortem | 4 | 2% | 98 | 100% | 2017-03-18 | 2017-04-04 | 2% | 100%
| Total | 98 | 100%

## SchedulePlanning
Table C49 Schedule Planning Template
| Student | Guillermo Vivaldo Vazquez |  |  |  | Date | 15/03/17
| Project | Alta Planes |  |  |  | Instructor | PEBM
|  | Plan |  |  | Actual
Day Number | Date Monday | Direct Min | Cumutative Minute | Cumulative Planned Value | Direct Min | Cumulative Minutes | Cumulative Earned Value | Adjusted Earned Value
1 | 2017-03-15 | 16 | 16 | 72% | 56 | 56 | 20%
2 | 2017-03-17 | 42 | 58 | 92% | 0 | 56 | 20%
3 | 2017-03-18 | 16 | 74 | 100% | 0 | 56 | 20%
4 | 2017-03-20 |  |  |  | 147.5 | 203.5 | 66%
5 | 2017-03-22 |  |  |  | 14.5 | 218 | 72%
6 | 2017-03-29 |  |  |  | 205.3 | 423.3 | 86%
7 | 2017-03-30 |  |  |  | 26.8 | 450.1 | 93%
8 | 2017-04-03 |  |  |  | 27.7 | 477.8 | 98%
9 | 2017-04-04 |  |  |  | 12 | 489.8 | 100%