## Project Plan Summary
PSP3 Project Plan Summary - Program 10A
Student | JUAN ALBERTO GUTIERREZ CANTO |  |  | Date | 2017-03-16
Program | Alta Maestros |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Summary
LOC/Hour |  | 31.93 | 12.77 | 18.48
Planned Time |  | 195 |  | 1562
Actual Time |  |  | 1281 | 3757
CPI (Planned/Actual Time) |  |  |  | 0.42
% Reused |  | 0 | 0 | 11.1
% New Reused |  | 0 | 0 | 0
Test Defects/KLOC |  | 4.95 | 47.62 | 18.89
Total Defects/KLOC |  | 54.46 | 163.27 | 90
Yield % |  | 87.9 | 14.6 | 44.4
% Appraisal COQ |  | 12.3 | 6.2 | 9.1
% Failure COQ |  | 6.1 | 40.2 | 22.1
COQ A/F Ratio |  | 2.01 | 0.15 | 0.41
Program Size (LOC)
Base(B) |  | 20 | 14
Deleted(D) |  | 5 | 3
Modified(M) |  | 10 | 2
Added(A) |  | 94 | 292
Reused(R) |  | 0 | 0 | 118
Total N&C (N) |  | 104 | 294 | 900
Total LOC(T) |  | 109 | 303 | 1063
Total New Reused |  | 0 | 0 | 0
Total Object LOC(E) |  | 86.43 | 283 | 816
UPI (70%)
LPI (70%)
Time in Phase (min.)
Planning |  | 38 | 50 | 337 | 11.5
High-level Design |  | 0 | 16 | 16 | 0.5
HLDR |  | 0 | 25 | 25 | 0.9
Design |  | 89 | 380 | 1147 | 39.2
Design Review |  | 12 | 85 | 176 | 6
Code |  | 27 | 100 | 304 | 10.4
Code Review |  | 12 | 85 | 89 | 3.1
Compile |  | 2 | 355 | 367 | 12.6
Test |  | 10 | 200 | 277 | 9.5
Postmortem |  | 5 | 70 | 184 | 6.3
Total |  | 195 | 1281 | 2922 | 100
UPI (70%)
LPI (70%)
PSP3 Project Plan Summary - Program 10A (Continued)
Student | JUAN ALBERTO GUTIERREZ CANTO |  |  | Date | 2017-03-16
Program | Alta Maestros |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Defects Injected
Planning |  | 0.2 | 6 | 7 | 8.6
High-level Design |  | 0 | 4 | 4 | 4.9
HLDR |  | 0 | 1 | 1 | 1.2
Design |  | 3.6 | 7 | 28 | 34.6
Design Review |  | 0 | 0 | 0 | 0
Code |  | 1.9 | 30 | 41 | 50.6
Code Review |  | 0 | 0 | 0 | 0
Compile |  | 0 | 0 | 0 | 0
Test |  | 0 | 0 | 0 | 0
Total Development |  | 5.6 | 48 | 81 | 100
Defects Removed
Planning |  | 0 | 0 | 0 | 0
High-level Design |  | 0 | 0 | 0 | 0
HLDR |  | 0 | 0 | 0 | 0
Design |  | 0.3 | 0 | 2 | 2.5
Design Review |  | 2.4 | 0 | 14 | 17.3
Code |  | 1 | 7 | 13 | 16
Code Review |  | 1.2 | 0 | 7 | 8.6
Compile |  | 0.2 | 27 | 28 | 34.6
Test |  | 0.5 | 14 | 17 | 21
Total Development |  | 5.6 | 48 | 81 | 100
After Development |  |  | 48 | 81
Defect Removal Efficiency
Def/Hr - HLDR |  | 0 | 0 | 0
Def/Hr - DLDR |  | 11.94 | 0 | 4.78
Def/Hr - CDR |  | 6.07 | 0 | 4.71
Def/Hr - Compile |  | 6.38 | 4.56 | 4.58
Def/Hr - Test |  | 3 | 4.2 | 3.68
DRL(HLDR/UT) |  | 0 | 0 | 0
DRL(DLDR/UT) |  | 3.98 | 0 | 1.3
DRL(CDR/UT) |  | 2.02 | 0 | 1.28
DRL(Compile/UT) |  | 2.13 | 1.09 | 1.24

## Size estimated template
Size Estimating Template
Student | Juan Alberto Gutierrez Canto |  |  |  | Date |  | 2017-03-16
Instructor | PEBM |  |  |  | Program# |  | Alta Maestros
BASE PROGRAM LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE SIZE (B) => |  |  |  |  | 20 |  | 14
LOC DELETED (D) => |  |  |  |  | 5 |  | 3
LOC MODIFIED (M) => |  |  |  |  | 10 |  | 2
OBJECT LOC
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC |  | C++ Object Size in LOC per Method
[9 empty] | Category | VS | S | M | L | VL
[9 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[9 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[9 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[9 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
(BA) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
TOTAL BASE ADDITIONS (BA) |  |  |  |  | 0 |  | 0 |  | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
Alta_Maestros() |  | I/O | 1 | VL | 28.9 |  | 143
Insert_Maestros() |  | Set-up | 1 | VL | 11.1 |  | 34
Query_Maestros() |  | Text | 1 | L | 36.4 |  | 44
actualizar_materias() |  | Logic | 1 | VL | 0 |  | 17
callback |  | I/O | 1 | VS | 0 |  | 9
insert_mtr_mst |  | Logic | 1 | VL | 0 |  | 26
print_archivo |  | I/O | 1 | VS | 0 |  | 8
(NO) subtotal from page 2 |  |  |  |  | 0 |  | 0
TOTAL NEW OBJECTS (NO) |  |  |  |  | 76.4 |  | 281
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
(R) subtotal from page 2 |  |  |  |  | 0 |  | 0
REUSED TOTAL (R) |  |  |  |  | 0 |  | 0
[5 empty] | Size |  | Time
Estimated Object LOC: |  |  | E = BA+NO+M |  | 86.4
Regression Parameter: |  |  | B0 |  | 0 |  | 0
Regression Parameter: |  |  | B1 |  | 1.2 |  | 2.26
Estimated New and Changed LOC: |  |  | N = B0 + B1` * E |  | 103.68
Estimated Total LOC: |  |  | T = N + B - D - M + R |  | 108.68
Estimated Total New Reuse (sum of * LOC): |  |  |  |  | 0
Estimated Total Developent Time: |  |  | Time = B0 + B1` * E |  |  |  | 81
Prediction Range: |  |  | Range |  | 0 |  | 0
Upper Prediction Interval: |  |  | UPI = N + Range |  | 0 |  | 0
Lower Prediction Interval: |  |  | LPI = N - Range |  | 0 |  | 0
Prediction Interval Percent |  |  |  |  | 70% |  | 70%
Method Selected |  |  |  |  | C |  | C
R^2 |  |  |  |  | 0 |  | 0
Size Estimating Template (continued)
Student | Juan Alberto Gutierrez Canto |  |  |  | Date |  | 2017-03-16
Instructor | PEBM |  |  |  | Program# |  | Alta Maestros
OBJECT LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC
C++ Object Size in LOC per Method
[15 empty] | Category | VS | S | M | L | VL
[15 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[15 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[15 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[15 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
[15 empty] | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
[15 empty] | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
SUBTOTAL BASE ADDITIONS (BA) => |  |  |  |  | 0 |  | 0
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
SUBTOTAL NEW OBJECTS (NO) => |  |  |  |  | 0 |  | 0
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
SUBTOTAL REUSED (R) => |  |  |  |  | 0 |  | 0

## Task Planning Template
| Project | Menu-principal |  |  |  | Instructor | PEBM
Task |  | Plan |  |  |  |  | Actual
Number | Name | Minutes | Planned Value | Cumulative Minutes | Cumulative Planned Value | Date Monday | Date | Earned Value | Cumulative Earned Value
1 | Planning | 38 | 19.49% | 38 | 19.49% | 2017-03-16 | 2017-03-16 | 19.49% | 19.49%
2 | High-level Design | 0 | 0% | 38 | 19.49% | 2017-03-16 | 2017-03-16 | 0% | 19.49%
3 | HLDR | 0 | 0% | 38 | 19.49% | 2017-03-16 | 2017-03-16 | 0% | 19.49%
4 | Design | 89 | 45.64% | 127 | 65.13% | 2017-03-17 | 2017-03-23 | 45.64% | 65.13%
5 | Design Review | 12 | 6.154% | 139 | 71.28% | 2017-03-17 | 2017-03-23 | 6.154% | 71.28%
6 | Code | 27 | 13.85% | 166 | 85.13% | 2017-03-18 | 2017-03-24 | 13.85% | 85.13%
7 | Code Review | 12 | 6.154% | 178 | 91.28% | 2017-03-18 | 2017-03-24 | 6.154% | 91.28%
8 | Compile | 2 | 1.026% | 180 | 92.31% | 2017-03-19 | 2017-03-28 | 1.026% | 92.31%
9 | Test | 10 | 5.128% | 190 | 97.44% | 2017-03-19 | 2017-03-29 | 5.128% | 97.44%
10 | Postmortem | 5 | 2.564% | 195 | 100% | 2017-03-19 | 2017-03-30 | 2.564% | 100%
| Total | 195 | 100% |  |  |  |  | 100%

## Schedule Planning Template
Table C49 Schedule Planning Template
| Student | Juan Alberto Gutierrez Canto |  |  |  | Date | 2017-03-16
| Project | Menu-principal |  |  |  | Instructor | PEBM
|  | Plan |  |  | Actual
Day Number | Date Monday | Direct Min | Cumutative Minute | Cumulative Planned Value | Direct Min | Cumulative Minutes | Cumulative Earned Value | Adjusted Earned Value
1 | 2017-03-16 | 38 | 38 | 19.49% | 91 | 91 | 19.49% | 0%
2 | 2017-03-17 | 101 | 139 | 71.28% | 0 | 91 | 19.49% | -51.79%
3 | 2017-03-18 | 39 | 178 | 91.28% | 0 | 91 | 19.49% | -71.79%
4 | 2017-03-19 | 17 | 195 | 100% | 0 | 91 | 19.49% | -80.51%
5 | 2017-03-20 | 0 | 195 | 100% | 0 | 91 | 19.49% | -80.51%
6 | 2017-03-21 | 0 | 195 | 100% | 0 | 91 | 19.49% | -80.51%
7 | 2017-03-22 | 0 | 195 | 100% | 0 | 91 | 19.49% | -80.51%
8 | 2017-03-23 | 0 | 195 | 100% | 465 | 556 | 71.28% | -28.72%
9 | 2017-03-24 | 0 | 195 | 100% | 130 | 686 | 91.28% | -8.718%
10 | 2017-03-25 | 0 | 195 | 100% | 0 | 686 | 91% | -9%
11 | 2017-03-26 | 0 | 195 | 100% | 0 | 686 | 91% | -9%
12 | 2017-03-27 | 0 | 195 | 100% | 0 | 686 | 91% | -9%
13 | 2017-03-28 | 0 | 195 | 100% | 355 | 1041 | 92% | -8%
14 | 2017-03-29 | 0 | 195 | 100% | 400 | 1441 | 97% | -3%
15 | 2017-03-30 | 0 | 195 | 100% | 70 | 1511 | 100% | 0%
0%