## Project Plan Summary
PSP3 Project Plan Summary - Program 10A
Student | BRENDA ROBLES ANTONIO |  |  | Date | 2017-03-12
Program | Menu maestros |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Summary
LOC/Hour |  | 41.51 | 9.98 | 25.77
Planned Time |  | 95 |  | 95
Actual Time |  |  | 186 | 186
CPI (Planned/Actual Time) |  |  |  | 0.51075
% Reused |  | 0 | 0 | 0
% New Reused |  | 0 | 0 | 0
Test Defects/KLOC |  | 2.92 | 0 | 2.67
Total Defects/KLOC |  | 26.24 | 96.77 | 32.09
Yield % |  | 88.9 | 100 | 91.7
% Appraisal COQ |  | 7.2 | 9.5 | 7.7
% Failure COQ |  | 5.7 | 0.8 | 4.6
COQ A/F Ratio |  | 1.28 | 11.53 | 1.67
Program Size (LOC)
Base(B) |  | 5 | 0
Deleted(D) |  | 0 | 0
Modified(M) |  | 0 | 0
Added(A) |  | 66 | 31
Reused(R) |  | 0 | 0 | 0
Total N&C (N) |  | 66 | 31 | 31
Total LOC(T) |  | 71 | 31 | 31
Total New Reused |  | 0 | 0 | 0
Total Object LOC(E) |  | 21.62 | 31 | 31
UPI (70%) |  | 119 |  |  |  | 228 | 100
LPI (70%) |  | 13 |  |  |  | 19.608 | 8.6
Time in Phase (min.)
Planning |  | 19 | 36 | 36 | 19.35%
High-level Design |  | 0 | 34 | 34 | 18.28%
HLDR |  | 0 | 13 | 13 | 6.989%
Design |  | 31 | 44 | 44 | 23.66%
Design Review |  | 3 | 10 | 10 | 5.376%
Code |  | 3 | 24 | 24 | 12.9%
Code Review |  | 19 | 7 | 7 | 3.763%
Compile |  | 0 | 0 | 0 | 0%
Test |  | 5 | 1 | 1 | 0.5376%
Postmortem |  | 13 | 16 | 16 | 8.602%
Total |  | 95 | 186 | 186 | 100%
UPI (70%) |  | 166
LPI (70%) |  | 25
PSP3 Project Plan Summary - Program (Continued)
Student | BRENDA ROBLES ANTONIO |  |  | Date | 2017-03-12
Program | Menú maestros |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Defects Injected
Planning |  | 0.6 | 3 | 3 | 100%
High-level Design |  | 0 | 0 | 0 | 0%
HLDR |  | 0 | 0 | 0 | 0%
Design |  | 0.2 | 0 | 0 | 0%
Design Review |  | 0 | 0 | 0 | 0%
Code |  | 1 | 0 | 0 | 0%
Code Review |  | 0 | 0 | 0 | 0%
Compile |  | 0 | 0 | 0 | 0%
Test |  | 0 | 0 | 0 | 0%
Total Development |  | 1.7 | 3 | 3 | 100%
Defects Removed
Planning |  | 0.4 | 3 | 3 | 100%
High-level Design |  | 0 | 0 | 0 | 0%
HLDR |  | 0 | 0 | 0 | 0%
Design |  | 0.2 | 0 | 0 | 0%
Design Review |  | 0.2 | 0 | 0 | 0%
Code |  | 0 | 0 | 0 | 0%
Code Review |  | 0.8 | 0 | 0 | 0%
Compile |  | 0 | 0 | 0 | 0%
Test |  | 0.2 | 0 | 0 | 0%
Total Development |  | 1.7 | 3 | 3 | 100%
After Development
Defect Removal Efficiency
Def/Hr - HLDR |  | 0 | 0 | 0
Def/Hr - DLDR |  | 3.48 | 0 | 0
Def/Hr - CDR |  | 12.91 | 0 | 0
Def/Hr - Compile |  | 0 | 0 | 0
Def/Hr - Test |  | 2.31 | 0 | 0
DRL(HLDR/UT) |  | 0 | 0 | 0
DRL(DLDR/UT) |  | 1.51 | 0 | 0
DRL(CDR/UT) |  | 5.58 | 0 | 0
DRL(Compile/UT) |  | 0 | 0 | 0

## Size estimated template
Size Estimating Template
Student | Brenda Robles Antonio |  |  |  | Date |  | 2017-03-12
Instructor | PEBM |  |  |  | Program# |  | Menú alumnos
BASE PROGRAM LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE SIZE (B) => |  |  |  |  | 5 |  | 0
LOC DELETED (D) => |  |  |  |  | 0 |  | 0
LOC MODIFIED (M) => |  |  |  |  | 0 |  | 0
OBJECT LOC
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC |  | C++ Object Size in LOC per Method
[9 empty] | Category | VS | S | M | L | VL
[9 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[9 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[9 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[9 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
(BA) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
TOTAL BASE ADDITIONS (BA) |  |  |  |  | 0 |  | 0 |  | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
Menu_maestros() |  | I/O | 1 | L | 21.6 |  | 28
int_main |  | I/O | 1 |  |  |  | 3
(NO) subtotal from page 2 |  |  |  |  | 0 |  | 0
TOTAL NEW OBJECTS (NO) |  |  |  |  | 21.6 |  | 31
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
(R) subtotal from page 2 |  |  |  |  | 0 |  | 0
REUSED TOTAL (R) |  |  |  |  | 0 |  | 0
[5 empty] | Size |  | Time
Estimated Object LOC: |  |  | E = BA+NO+M |  | 21.6
Regression Parameter: |  |  | B0 |  | 0 |  | 0
Regression Parameter: |  |  | B1 |  | 1.2 |  | 2.26
Estimated New and Changed LOC: |  |  | N = B0 + B1` * E |  | 25.92
Estimated Total LOC: |  |  | T = N + B - D - M + R |  | 30.92
Estimated Total New Reuse (sum of * LOC): |  |  |  |  | 0
Estimated Total Developent Time: |  |  | Time = B0 + B1` * E |  |  |  | 81
Prediction Range: |  |  | Range |  | 0 |  | 0
Upper Prediction Interval: |  |  | UPI = N + Range |  | 0 |  | 0
Lower Prediction Interval: |  |  | LPI = N - Range |  | 0 |  | 0
Prediction Interval Percent |  |  |  |  | 70% |  | 70%
Method Selected |  |  |  |  | C |  | C
R^2 |  |  |  |  | 0 |  | 0
Size Estimating Template (continued)
Student | Brenda Robles Antonio |  |  |  | Date |  | 2017-03-12
Instructor | PEBM |  |  |  | Program# |  | Menú alumnos
OBJECT LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC
C++ Object Size in LOC per Method
[15 empty] | Category | VS | S | M | L | VL
[15 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[15 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[15 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[15 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
[15 empty] | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
[15 empty] | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
SUBTOTAL BASE ADDITIONS (BA) => |  |  |  |  | 0 |  | 0
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
SUBTOTAL NEW OBJECTS (NO) => |  |  |  |  | 0 |  | 0
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
SUBTOTAL REUSED (R) => |  |  |  |  | 0 |  | 0

## Task Planning Template
| Project | Menu-maestros |  |  |  | Instructor | PEBM
Task |  | Plan |  |  |  |  | Actual
Number | Name | Minutes | Planned Value | Cumulative Minutes | Cumulative Planned Value | Date Monday | Date | Earned Value | Cumulative Earned Value
1 | Planning | 19 | 20.21% | 19 | 20.21% | 2017-03-12 | 2017-03-12 | 20.21% | 20.21%
2 | High-level Design | 0 | 0% | 19 | 20.21% | 2017-03-12 | 2017-03-12 | 20.21% | 40.43%
3 | HLDR | 0 | 0% | 19 | 20.21% | 2017-03-12 | 2017-03-12 | 20.21% | 60.64%
4 | Design | 31 | 32.98% | 50 | 53.19% | 2017-03-12 | 2017-03-12 | 53.19% | 113.8%
5 | Design Review | 3 | 3.191% | 53 | 56.38% | 2017-03-21 | 2017-03-22 | 56.38% | 170.2%
6 | Code | 19 | 20.21% | 72 | 76.6% | 2017-03-21 | 2017-03-22 | 76.6% | 246.8%
7 | Code Review | 4 | 4.255% | 76 | 80.85% | 2017-03-21 | 2017-03-22 | 80.85% | 327.7%
8 | Compile | 0 | 0% | 76 | 80.85% | 2017-03-21 | 2017-03-22 | 80.85% | 408.5%
9 | Test | 5 | 5.319% | 81 | 86.17% | 2017-03-21 | 2017-03-22 | 86.17% | 494.7%
10 | Postmortem | 13 | 13.83% | 94 | 100% | 2017-03-21 | 2017-03-30 | 100% | 594.7%
| Total | 94 | 100%

## Schedule Planning Template
Table C49 Schedule Planning Template
| Student | Brenda Robles Antonio |  |  |  | Date | 2017-03-12
| Project | Menu-maestros |  |  |  | Instructor | PEBM
|  | Plan |  |  | Actual
Day Number | Date Monday | Direct Min | Cumutative Minute | Cumulative Planned Value | Direct Min | Cumulative Minutes | Cumulative Earned Value | Adjusted Earned Value
1 | 2017-03-12 | 50 | 50 | 53.19% | 127 | 127 | 53.19% | 68.28%
2 | 2017-03-21 | 44 | 94 | 100% | 59 | 186 | 100% | 31.72%