## Project Plan Summary
PSP3 Project Plan Summary - Program
Student | Jesús Alberto Goiz Barrales |  |  | Date | 2017-03-20
Program | Menú-Alumnos |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Summary
LOC/Hour |  | 29.95 | 2.66 | 21.62
Planned Time |  | 104 |  | 1014
Actual Time |  |  | 68 | 1336
CPI (Planned/Actual Time) |  |  |  | 0.76
% Reused |  | 0 | 0 | 35.3
% New Reused |  | 0 | 233.3 | 2.7
Test Defects/KLOC |  | 7.81 | 0 | 7.72
Total Defects/KLOC |  | 148.44 | 7000 | 227.8
Yield % |  | 81.6 | 100 | 88.1
% Appraisal COQ |  | 21.2 | 32.4 | 22.3
% Failure COQ |  | 10.3 | 4.4 | 9.8
COQ A/F Ratio |  | 2.05 | 7.33 | 2.28
Program Size (LOC)
Base(B) |  | 30 | 48
Deleted(D) |  | 8 | 0
Modified(M) |  | 10 | 3
Added(A) |  | 66 | 0
Reused(R) |  | 0 | 0 | 270
Total N&C (N) |  | 76 | 3 | 259
Total LOC(T) |  | 88 | 48 | 765
Total New Reused |  | 0 | 7 | 7
Total Object LOC(E) |  | 41 | 48 | 342
UPI (70%) |  | 102
LPI (70%) |  | 50
Time in Phase (min.)
Planning |  | 42 | 9 | 196 | 23.9
High-level Design |  | 0 | 5 | 0 | 0
HLDR |  | 0 | 5 | 0 | 0
Design |  | 31 | 32 | 163 | 19.9
Design Review |  | 18 | 10 | 83 | 10.2
Code |  | 20 | 29 | 114 | 13.8
Code Review |  | 15 | 17 | 82 | 9.9
Compile |  | 4 | 1 | 16 | 1.9
Test |  | 13 | 2 | 54 | 6.6
Postmortem |  | 13 | 92 | 144 | 16.9
Total |  | 156 | 202 | 852 | 103.1
UPI (70%) |  | 239
LPI (70%) |  | 71
PSP3 Project Plan Summary - Program N/A (Continued)
Student | Jesús Alberto Goiz Barrales |  |  | Date | 2017-03-20
Program | Menú-Alumnos |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Defects Injected
Planning |  | 0 | 0 | 1 | 0
High-level Design |  | 0 | 0 | 0 | 0
HLDR |  | 0 | 0 | 0 | 0
Design |  | 1.5 | 13 | 18 | 30.5
Design Review |  | 0.6 | 0 | 2 | 3.4
Code |  | 9.2 | 8 | 39 | 66.1
Code Review |  | 0 | 0 | 0 | 0
Compile |  | 0 | 0 | 0 | 0
Test |  | 0 | 0 | 0 | 0
Total Development |  | 11.3 | 21 | 60 | 100
Defects Removed
Planning |  | 0 | 0 | 0 | 0
High-level Design |  | 0 | 0 | 0 | 0
HLDR |  | 0 | 0 | 0 | 0
Design |  | 0 | 0 | 0 | 0
Design Review |  | 2.1 | 13 | 20 | 33.9
Code |  | 0 | 0 | 0 | 0
Code Review |  | 7.1 | 8 | 32 | 54.2
Compile |  | 1.5 | 0 | 5 | 8.5
Test |  | 0.6 | 0 | 2 | 3.4
Total Development |  | 11.3 | 21 | 59 | 100
After Development |  |  | ????? | ?????
Defect Removal Efficiency
Def/Hr - HLDR |  | 0 | 0 | 0
Def/Hr - DLDR |  | 5.6 | 78 | 14.39
Def/Hr - CDR |  | 21.85 | 28.24 | 23.55
Def/Hr - Compile |  | 19.91 | 0 | 19.05
Def/Hr - Test |  | 2.24 | 0 | 2.2
DRL(HLDR/UT) |  | 0 | 0 | 0
DRL(DLDR/UT) |  | 2.5 | 34.09 | 6.53
DRL(CDR/UT) |  | 9.76 | 12.34 | 10.69
DRL(Compile/UT) |  | 8.89 | 0 | 8.64

## Size estimated template
Size Estimating Template
Student | Jesús Alberto Goiz Barrales |  |  |  | Date |  | 2017-03-20
Instructor | PEBM |  |  |  | Program# |  | N/A
BASE PROGRAM LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE SIZE (B) => |  |  |  |  | 30 |  | 48
LOC DELETED (D) => |  |  |  |  | 8 |  | 0
LOC MODIFIED (M) => |  |  |  |  | 10 |  | 3
OBJECT LOC
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC |  | C++ Object Size in LOC per Method
[9 empty] | Category | VS | S | M | L | VL
[9 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[9 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[9 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[9 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
(BA) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
TOTAL BASE ADDITIONS (BA) |  |  |  |  | 0 |  | 0 |  | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
ABC_Alumnos |  | VOID | I/O | L | 22 |  | 39
Main |  | VOID | I/O | VS | 9.01 |  | 6
(NO) subtotal from page 2 |  |  |  |  | 0 |  | 0
TOTAL NEW OBJECTS (NO) |  |  |  |  | 31.01 |  | 45
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
(R) subtotal from page 2 |  |  |  |  | 0 |  | 0
REUSED TOTAL (R) |  |  |  |  | 0 |  | 0
[5 empty] | Size |  | Time
Estimated Object LOC: |  |  | E = BA+NO+M |  | 41.01
Regression Parameter: |  |  | B0 |  | 0 |  | 0
Regression Parameter: |  |  | B1 |  | 1.2 |  | 2.26
Estimated New and Changed LOC: |  |  | N = B0 + B1` * E |  | 49.212
Estimated Total LOC: |  |  | T = N + B - D - M + R |  | 61.212
Estimated Total New Reuse (sum of * LOC): |  |  |  |  | 0
Estimated Total Developent Time: |  |  | Time = B0 + B1` * E |  |  |  | 81
Prediction Range: |  |  | Range |  | 0 |  | 0
Upper Prediction Interval: |  |  | UPI = N + Range |  | 0 |  | 0
Lower Prediction Interval: |  |  | LPI = N - Range |  | 0 |  | 0
Prediction Interval Percent |  |  |  |  | 70% |  | 70%
Method Selected |  |  |  |  | C |  | C
R^2 |  |  |  |  | 0 |  | 0
Size Estimating Template (continued)
Student | Jesús Alberto Goiz Barrales |  |  |  | Date |  | 2017-03-20
Instructor | PEBM |  |  |  | Program# |  | N/A
OBJECT LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC
C++ Object Size in LOC per Method
[15 empty] | Category | VS | S | M | L | VL
[15 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[15 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[15 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[15 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
[15 empty] | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
[15 empty] | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
SUBTOTAL BASE ADDITIONS (BA) => |  |  |  |  | 0 |  | 0
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
SUBTOTAL NEW OBJECTS (NO) => |  |  |  |  | 0 |  | 0
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
SUBTOTAL REUSED (R) => |  |  |  |  | 0 |  | 0

## Task Planning Template
| Project | Menú-Alumnos |  |  |  | Instructor | PEBM
Task |  | Plan |  |  |  |  | Actual
Number | Name | Minutes | Planned Value | Cumulative Minutes | Cumulative Planned Value | Date Monday | Date | Earned Value | Cumulative Earned Value
1 | Planning | 42 | 26.92% | 42 | 26.92% | 2017-03-20 | 2017-03-20 | 26.92% | 26.92%
2 | High-level Design | 0 | 0% | 42 | 26.92% | 2017-03-20 | 2017-03-20 | 0% | 26.92%
3 | HLDR | 0 | 0% | 42 | 26.92% | 2017-03-20 | 2017-03-20 | 0% | 26.92%
4 | Design | 31 | 19.87% | 73 | 46.79% | 2017-03-20 | 2017-03-20 | 19.87% | 46.79%
5 | Design Review | 18 | 11.54% | 91 | 58.33% | 2017-03-20 | 2017-03-23 | 11.54% | 58.33%
6 | Code | 20 | 12.82% | 111 | 71.15% | 2017-03-22 | 2017-03-23 | 12.82% | 71.15%
7 | Code Review | 15 | 9.615% | 126 | 80.77% | 2017-03-22 | 2017-03-23 | 9.615% | 80.77%
8 | Compile | 4 | 2.564% | 130 | 83.33% | 2017-03-22 | 2017-03-26 | 2.564% | 83.33%
9 | Test | 13 | 8.333% | 143 | 91.67% | 2017-03-22 | 2017-03-26 | 8.333% | 91.67%
10 | Postmortem | 13 | 8.333% | 156 | 100% | 2017-03-22 | 2017-03-26 | 8.333% | 100%
| Total | 156 | 100%

## Schedule Planning Template
Table C49 Schedule Planning Template
| Student | Jesús Alberto Goiz Barrales |  |  |  | Date | 2017-03-20
| Project | Menú-Alumnos |  |  |  | Instructor | PEBM
|  | Plan |  |  | Actual
Day Number | Date Monday | Direct Min | Cumutative Minute | Cumulative Planned Value | Direct Min | Cumulative Minutes | Cumulative Earned Value
4 | 2017-03-20 | 42 | 42 | 26.92% | 9 | 9 | 26.92%
4 | 2017-03-20 | 0 | 42 | 26.92% | 5 | 14 | 26.92%
4 | 2017-03-20 | 0 | 42 | 26.92% | 5 | 19 | 26.92%
4 | 2017-03-20 | 31 | 73 | 46.79% | 32 | 51 | 46.79%
4 | 2017-03-20 | 18 | 91 | 58.33% | 10 | 61 | 58.33%
7 | 2017-03-23 | 20 | 111 | 71.15% | 29 | 90 | 71.15%
7 | 2017-03-23 | 15 | 126 | 80.77% | 17 | 107 | 80.77%
3 | 2017-03-26 | 4 | 130 | 83.33% | 1 | 108 | 83.33%
3 | 2017-03-26 | 13 | 143 | 91.67% | 2 | 110 | 91.67%
3 | 2017-03-26 | 13 | 156 | 100% | 92 | 202 | 100%