## Project Plan Summary
PSP3 Project Plan Summary - Program 10A
Student | JUAN ALBERTO GUTIERREZ CANTO |  |  | Date | 2017-03-15
Program | Menú principal |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Summary
LOC/Hour |  | 31.93 | 10.31 | 21.78
Planned Time |  | 81 |  | 1448
Actual Time |  |  | 384 | 2686
CPI (Planned/Actual Time) |  |  |  | 0.54
% Reused |  | 0 | 0 | 14.3
% New Reused |  | 0 | 0 | 0
Test Defects/KLOC |  | 4.95 | 242.42 | 28.27
Total Defects/KLOC |  | 54.46 | 348.48 | 83.33
Yield % |  | 87.9 | 26.1 | 62.5
% Appraisal COQ |  | 12.3 | 18.8 | 13.6
% Failure COQ |  | 6.1 | 12.5 | 7.4
COQ A/F Ratio |  | 2.01 | 1.5 | 1.83
Program Size (LOC)
Base(B) |  | 20 | 9
Deleted(D) |  | 5 | 7
Modified(M) |  | 7 | 4
Added(A) |  | 36 | 62
Reused(R) |  | 0 | 0 | 118
Total N&C (N) |  | 43 | 66 | 672
Total LOC(T) |  | 51 | 64 | 824
Total New Reused |  | 0 | 0 | 0
Total Object LOC(E) |  | 35.9 | 59 | 592
UPI (70%)
LPI (70%)
Time in Phase (min.)
Planning |  | 16 | 70 | 357 | 19.3
High-level Design |  | 0 | 18 | 18 | 1
HLDR |  | 0 | 10 | 10 | 0.5
Design |  | 37 | 98 | 765 | 41.3
Design Review |  | 5 | 42 | 133 | 7.2
Code |  | 11 | 38 | 242 | 13.1
Code Review |  | 5 | 30 | 119 | 6.4
Compile |  | 1 | 4 | 16 | 0.9
Test |  | 4 | 44 | 121 | 6.6
Postmortem |  | 2 | 30 | 71 | 3.8
Total |  | 81 | 384 | 1852 | 100
UPI (70%)
LPI (70%)
PSP3 Project Plan Summary - Program 10A (Continued)
Student | 94419-JUAN ALBERTO GUTIERREZ CANTO |  |  | Date | 2017-03-15
Program | Menú Principal |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | c++
|  | Plan | Actual | To Date | To Date%
Defects Injected
Planning |  | 0.1 | 1 | 2 | 3.6
High-level Design |  | 0 | 5 | 5 | 8.9
HLDR |  | 0 | 2 | 2 | 3.6
Design |  | 1.5 | 14 | 35 | 62.5
Design Review |  | 0 | 0 | 0 | 0
Code |  | 0.8 | 1 | 12 | 21.4
Code Review |  | 0 | 0 | 0 | 0
Compile |  | 0 | 0 | 0 | 0
Test |  | 0 | 0 | 0 | 0
Total Development |  | 2.3 | 23 | 56 | 100
Defects Removed
Planning |  | 0 | 0 | 0 | 0
High-level Design |  | 0 | 0 | 0 | 0
HLDR |  | 0 | 6 | 6 | 10.7
Design |  | 0.1 | 0 | 2 | 3.6
Design Review |  | 1 | 0 | 14 | 25
Code |  | 0.4 | 0 | 6 | 10.7
Code Review |  | 0.5 | 0 | 7 | 12.5
Compile |  | 0.1 | 1 | 2 | 3.6
Test |  | 0.2 | 16 | 19 | 33.9
Total Development |  | 2.3 | 23 | 56 | 100
After Development |  |  | 23 | 56
Defect Removal Efficiency
Def/Hr - HLDR |  | 0 | 36 | 36
Def/Hr - DLDR |  | 11.94 | 0 | 6.33
Def/Hr - CDR |  | 6.07 | 0 | 3.53
Def/Hr - Compile |  | 6.38 | 15 | 7.45
Def/Hr - Test |  | 3 | 21.82 | 9.39
DRL(HLDR/UT) |  | 0 | 1.65 | 3.83
DRL(DLDR/UT) |  | 3.98 | 0 | 0.67
DRL(CDR/UT) |  | 2.02 | 0 | 0.38
DRL(Compile/UT) |  | 2.13 | 0.69 | 0.79

## Size estimated template
Size Estimating Template
Student | Juan Alberto Gutierrez Canto |  |  |  | Date |  | 2017-03-10
Instructor | PEBM |  |  |  | Program# |  | Menú principal
BASE PROGRAM LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE SIZE (B) => |  |  |  |  | 20 |  | 9
LOC DELETED (D) => |  |  |  |  | 5 |  | 11
LOC MODIFIED (M) => |  |  |  |  | 7 |  | 4
OBJECT LOC
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC |  | C++ Object Size in LOC per Method
[9 empty] | Category | VS | S | M | L | VL
[9 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[9 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[9 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[9 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
(BA) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
TOTAL BASE ADDITIONS (BA) |  |  |  |  | 0 |  | 0 |  | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
Menu_principal() |  | VOID | I/O | VL | 28.93 |  | 55
(NO) subtotal from page 2 |  |  |  |  | 0 |  | 0
TOTAL NEW OBJECTS (NO) |  |  |  |  | 28.93 |  | 55
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
(R) subtotal from page 2 |  |  |  |  | 0 |  | 0
REUSED TOTAL (R) |  |  |  |  | 0 |  | 0
[5 empty] | Size |  | Time
Estimated Object LOC: |  |  | E = BA+NO+M |  | 35.93
Regression Parameter: |  |  | B0 |  | 0 |  | 0
Regression Parameter: |  |  | B1 |  | 1.2 |  | 2.26
Estimated New and Changed LOC: |  |  | N = B0 + B1` * E |  | 43.116
Estimated Total LOC: |  |  | T = N + B - D - M + R |  | 51.116
Estimated Total New Reuse (sum of * LOC): |  |  |  |  | 0
Estimated Total Developent Time: |  |  | Time = B0 + B1` * E |  |  |  | 81
Prediction Range: |  |  | Range |  | 0 |  | 0
Upper Prediction Interval: |  |  | UPI = N + Range |  | 0 |  | 0
Lower Prediction Interval: |  |  | LPI = N - Range |  | 0 |  | 0
Prediction Interval Percent |  |  |  |  | 70% |  | 70%
Method Selected |  |  |  |  | C |  | C
R^2 |  |  |  |  | 0 |  | 0
Size Estimating Template (continued)
Student | Juan Alberto Gutierrez Canto |  |  |  | Date |  | 2017-03-10
Instructor | PEBM |  |  |  | Program# |  | Menú principal
OBJECT LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC
C++ Object Size in LOC per Method
[15 empty] | Category | VS | S | M | L | VL
[15 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[15 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[15 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[15 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
[15 empty] | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
[15 empty] | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
SUBTOTAL BASE ADDITIONS (BA) => |  |  |  |  | 0 |  | 0
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
SUBTOTAL NEW OBJECTS (NO) => |  |  |  |  | 0 |  | 0
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
SUBTOTAL REUSED (R) => |  |  |  |  | 0 |  | 0

## Task Planning Template
| Project | Menu-principal |  |  |  | Instructor | PEBM
Task |  | Plan |  |  |  |  | Actual
Number | Name | Minutes | Planned Value | Cumulative Minutes | Cumulative Planned Value | Date Monday | Date | Earned Value | Cumulative Earned Value
1 | Planning | 16 | 19.75% | 16 | 19.75% | 2017-03-10 | 2017-10-03 | 19.75% | 19.75%
2 | High-level Design | 0 | 0% | 16 | 19.75% | 2017-03-15 | 2017-03-15 | 0% | 19.75%
3 | HLDR | 0 | 0% | 16 | 19.75% | 2017-03-15 | 2017-03-15 | 0% | 19.75%
4 | Design | 37 | 45.68% | 53 | 65.43% | 2017-03-15 | 2017-03-15 | 45.68% | 65.43%
5 | Design Review | 5 | 6.173% | 58 | 71.6% | 2017-03-15 | 2017-03-15 | 6.173% | 71.6%
6 | Code | 11 | 13.58% | 69 | 85.19% | 2017-03-16 | 2017-03-16 | 13.58% | 85.19%
7 | Code Review | 5 | 6.173% | 74 | 91.36% | 2017-03-16 | 2017-03-16 | 6.173% | 91.36%
8 | Compile | 1 | 1.235% | 75 | 92.59% | 2017-03-17 | 2017-03-17 | 1.235% | 92.59%
9 | Test | 4 | 4.938% | 79 | 97.53% | 2017-03-17 | 2017-03-30 | 4.938% | 97.53%
10 | Postmortem | 2 | 2.469% | 81 | 100% | 2017-03-17 | 2017-03-30 | 2.469% | 100%
| Total | 81 | 100% |  |  |  |  | 100%

## Schedule Planning Template
Table C49 Schedule Planning Template
| Student | Juan Alberto Gutierrez Canto |  |  |  | Date | 2017-03-10
| Project | Menu-principal |  |  |  | Instructor | PEBM
|  | Plan |  |  | Actual
Day Number | Date Monday | Direct Min | Cumutative Minute | Cumulative Planned Value | Direct Min | Cumulative Minutes | Cumulative Earned Value | Adjusted Earned Value
1 | 2017-03-10 | 16 | 16 | 19.75% | 70 | 70 | 20% | 0.2469%
2 | 2017-03-15 | 42 | 58 | 71.6% | 126 | 196 | 72% | 0.3951%
3 | 2017-03-16 | 16 | 74 | 91.36% | 68 | 264 | 91% | -0.358%
4 | 2017-03-17 | 7 | 81 | 100% | 4 | 268 | 92% | -8%
5 | 2017-03-30 | 0 | 81 | 100% | 70 | 338 | 100% | 0%