## Project Plan Summary
PSP3 Project Plan Summary - Program
Student | JAGB |  |  | Date | 2017-05-01
Program | Baja Alumnos |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Summary
LOC/Hour |  | 29.95 | 26.6 | 18.67
Planned Time |  | 155 |  | 1100
Actual Time |  |  | 188 | 1456
CPI (Planned/Actual Time) |  |  |  | 0.75
% Reused |  | 0 | 0 | 31.1
% New Reused |  | 0 | 140 | 2.7
Test Defects/KLOC |  | 7.81 | 200 | 11.49
Total Defects/KLOC |  | 148.44 | 200 | 149.43
Yield % |  | 81.6 | 0 | 79.5
% Appraisal COQ |  | 21.2 | 27.1 | 22.5
% Failure COQ |  | 10.3 | 29.3 | 14.6
COQ A/F Ratio |  | 2.05 | 0.93 | 1.55
Program Size (LOC)
Base(B) |  | 137 | 146
Deleted(D) |  | 0 | 0
Modified(M) |  | 0 | 0
Added(A) |  | 99 | 5
Reused(R) |  | 0 | 0 | 270
Total N&C (N) |  | 99 | 5 | 261
Total LOC(T) |  | 236 | 151 | 868
Total New Reused |  | 0 | 7 | 7
Total Object LOC(E) |  | 137 | 146 | 440
UPI (70%) |  | 133
LPI (70%) |  | 66
Time in Phase (min.)
Planning |  | 20 | 10 | 197 | 23.5
High-level Design |  | 5 | 5 | 0 | 0
HLDR |  | 5 | 5 | 0 | 0
Design |  | 50 | 20 | 151 | 18
Design Review |  | 25 | 23 | 96 | 11.5
Code |  | 30 | 27 | 112 | 13.3
Code Review |  | 20 | 28 | 93 | 11
Compile |  | 1 | 3 | 18 | 2.1
Test |  | 15 | 52 | 104 | 12.5
Postmortem |  | 25 | 15 | 67 | 8
Total |  | 196 | 188 | 838 | 99.9
UPI (70%) |  | 239
LPI (70%) |  | 71
PSP3 Project Plan Summary - Program N/A (Continued)
Student | JAGB |  |  | Date | 2017-05-01
Program | Baja Alumnos |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Defects Injected
Planning |  | 0 | 0 | 0 | 0
High-level Design |  | 0 | 0 | 0 | 0
HLDR |  | 0 | 0 | 0 | 0
Design |  | 1.9 | 0 | 5 | 12.8
Design Review |  | 0.8 | 0 | 2 | 5.1
Code |  | 12 | 1 | 32 | 82.1
Code Review |  | 0 | 0 | 0 | 0
Compile |  | 0 | 0 | 0 | 0
Test |  | 0 | 0 | 0 | 0
Total Development |  | 14.7 | 1 | 39 | 100
Defects Removed
Planning |  | 0 | 0 | 0 | 0
High-level Design |  | 0 | 0 | 0 | 0
HLDR |  | 0 | 0 | 0 | 0
Design |  | 0 | 0 | 0 | 0
Design Review |  | 1.8 | 0 | 7 | 17.9
Code |  | 0 | 0 | 0 | 0
Code Review |  | 6.3 | 0 | 24 | 61.5
Compile |  | 1.3 | 0 | 5 | 12.8
Test |  | 0.5 | 1 | 3 | 7.7
Total Development |  | 9.9 | 1 | 39 | 100
After Development |  |  | ????? | ?????
Defect Removal Efficiency
Def/Hr - HLDR |  | 0 | 0 | 0
Def/Hr - DLDR |  | 6 | 0 | 4.36
Def/Hr - CDR |  | 23.4 | 0 | 15.56
Def/Hr - Compile |  | 21.32 | 0 | 16.9
Def/Hr - Test |  | 2.4 | 1.15 | 1.72
DRL(HLDR/UT) |  | 0 | 0 | 0
DRL(DLDR/UT) |  | 2.5 | 0 | 2.53
DRL(CDR/UT) |  | 9.76 | 0 | 9.03
DRL(Compile/UT) |  | 8.89 | 0 | 9.81

## Size estimated template
Size Estimating Template
Student | JAGB |  |  |  | Date |  | 2017-05-01
Instructor | PEBM |  |  |  | Program# |  | N/A
BASE PROGRAM LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE SIZE (B) => |  |  |  |  | 137
LOC DELETED (D) => |  |  |  |  | 0
LOC MODIFIED (M) => |  |  |  |  | 0
OBJECT LOC
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC |  | C++ Object Size in LOC per Method
[9 empty] | Category | VS | S | M | L | VL
[9 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[9 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[9 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[9 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
(BA) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
TOTAL BASE ADDITIONS (BA) |  |  |  |  | 0 |  | 0 |  | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
baja_alumnos |  | I/O | 1 | VL | 29 |  | 61
Query_Alumno() |  | Text | 1 | L | 36 |  | 45
borrar_alumnos() |  | Text | 1 | L | 36 |  | 20
borrar_cursa() |  | Text | 1 | L | 36 |  | 20
(NO) subtotal from page 2 |  |  |  |  | 0 |  | 0
TOTAL NEW OBJECTS (NO) |  |  |  |  | 137 |  | 146
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
(R) subtotal from page 2 |  |  |  |  | 0 |  | 0
REUSED TOTAL (R) |  |  |  |  | 0 |  | 0
[5 empty] | Size |  | Time
Estimated Object LOC: |  |  | E = BA+NO+M |  | 137
Regression Parameter: |  |  | B0 |  | 0 |  | 0
Regression Parameter: |  |  | B1 |  | 1.2 |  | 2.26
Estimated New and Changed LOC: |  |  | N = B0 + B1` * E |  | 164.4
Estimated Total LOC: |  |  | T = N + B - D - M + R |  | 301.4
Estimated Total New Reuse (sum of * LOC): |  |  |  |  | 0
Estimated Total Developent Time: |  |  | Time = B0 + B1` * E |  |  |  | 81
Prediction Range: |  |  | Range |  | 0 |  | 0
Upper Prediction Interval: |  |  | UPI = N + Range |  | 0 |  | 0
Lower Prediction Interval: |  |  | LPI = N - Range |  | 0 |  | 0
Prediction Interval Percent |  |  |  |  | 70% |  | 70%
Method Selected |  |  |  |  | C |  | C
R^2 |  |  |  |  | 0 |  | 0
Size Estimating Template (continued)
Student | JAGB |  |  |  | Date |  | 2017-05-01
Instructor | PEBM |  |  |  | Program# |  | N/A
OBJECT LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC
C++ Object Size in LOC per Method
[15 empty] | Category | VS | S | M | L | VL
[15 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[15 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[15 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[15 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
[15 empty] | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
[15 empty] | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
SUBTOTAL BASE ADDITIONS (BA) => |  |  |  |  | 0 |  | 0
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
SUBTOTAL NEW OBJECTS (NO) => |  |  |  |  | 0 |  | 0
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
SUBTOTAL REUSED (R) => |  |  |  |  | 0 |  | 0

## Task Planning Template
| Project | Baja Alumnos |  |  |  | Instructor | PEBM
Task |  | Plan |  |  |  |  | Actual
Number | Name | Minutes | Planned Value | Cumulative Minutes | Cumulative Planned Value | Date Monday | Date | Earned Value | Cumulative Earned Value
1 | Planning | 20 | 10.2% | 20 | 10.2% | 2017-05-01 | 2017-05-01 | 10.2% | 10.2%
2 | High-level Design | 5 | 2.551% | 25 | 12.76% | 2017-05-01 | 2017-05-01 | 2.551% | 12.76%
3 | HLDR | 5 | 2.551% | 30 | 15.31% | 2017-05-01 | 2017-05-01 | 2.551% | 15.31%
4 | Design | 50 | 25.51% | 80 | 40.82% | 2017-05-01 | 2017-05-01 | 25.51% | 40.82%
5 | Design Review | 25 | 12.76% | 105 | 53.57% | 2017-05-01 | 2017-05-01 | 12.76% | 53.57%
6 | Code | 30 | 15.31% | 135 | 68.88% | 2017-05-02 | 2017-05-09 | 15.31% | 68.88%
7 | Code Review | 20 | 10.2% | 155 | 79.08% | 2017-05-02 | 2017-05-09 | 10.2% | 79.08%
8 | Compile | 1 | 0.5102% | 156 | 79.59% | 2017-05-02 | 2017-05-09 | 0.5102% | 79.59%
9 | Test | 15 | 7.653% | 171 | 87.24% | 2017-05-02 | 2017-05-09 | 7.653% | 87.24%
10 | Postmortem | 25 | 12.76% | 196 | 100% | 2017-05-02 | 10/05/¦7 | 12.76% | 100%
| Total | 196 | 100%

## Schedule Planning Template
Table C49 Schedule Planning Template
| Student | JAGB |  |  |  | Date | 2017-05-01
| Project | Baja Alumnos |  |  |  | Instructor | PEBM
|  | Plan |  |  | Actual
Day Number | Date Monday | Direct Min | Cumutative Minute | Cumulative Planned Value | Direct Min | Cumulative Minutes | Cumulative Earned Value
4 | 2017-05-01 | 20 | 20 | 10.2% | 10 | 10 | 10.2%
4 | 2017-05-01 | 5 | 25 | 12.76% | 5 | 15 | 12.76%
4 | 2017-05-01 | 5 | 30 | 15.31% | 5 | 20 | 15.31%
4 | 2017-05-01 | 50 | 80 | 40.82% | 20 | 40 | 40.82%
4 | 2017-05-01 | 25 | 105 | 53.57% | 23 | 63 | 53.57%
|  | 30 | 135 | 68.88% | 27 | 90 | 68.88%
|  | 20 | 155 | 79.08% | 28 | 118 | 79.08%
|  | 1 | 156 | 79.59% | 3 | 121 | 79.59%
|  | 15 | 171 | 87.24% | 52 | 173 | 87.24%
|  | 25 | 196 | 100% | 15 | 188 | 100%