## Project Plan Summary
PSP3 Project Plan Summary - Program
Student | RMM |  |  | Date | 2017-05-03
Program | Baja Maestros |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Summary
LOC/Hour |  | 24.63 | 57.71 | 25.96
Planned Time |  | 257 |  | 1737
Actual Time |  |  | 167 | 1699
CPI (Planned/Actual Time) |  |  |  | 1.02
% Reused |  | 0 | 0 | 0
% New Reused |  | 0 | 0 | 23.1
Test Defects/KLOC |  | 6.6 | 6.21 | 6.47
Total Defects/KLOC |  | 66.01 | 6.21 | 45.26
Yield % |  | 90 | 0 | 85.7
% Appraisal COQ |  | 24 | 6.9 | 21.4
% Failure COQ |  | 13.9 | 21.4 | 15.1
COQ A/F Ratio |  | 1.73 | 0.32 | 1.42
Program Size (LOC)
Base(B) |  | 23 | 0
Deleted(D) |  | 2 | 0
Modified(M) |  | 5 | 0
Added(A) |  | 100 | 161
Reused(R) |  | 0 | 0 | 0
Total N&C (N) |  | 105 | 161 | 464
Total LOC(T) |  | 121 | 161 | 845
Total New Reused |  | 0 | 0 | 107
Total Object LOC(E) |  | 129.42 | 156 | 535
UPI (70%) |  | 127
LPI (70%) |  | 84
Time in Phase (min.)
Planning |  | 45 | 20 | 180 | 16.8
High-level Design |  | 0 | 6 | 6 | 0.6
HLDR |  | 0 | 2 | 2 | 0.2
Design |  | 57 | 28 | 229 | 21.3
Design Review |  | 23 | 7 | 90 | 8.3
Code |  | 47 | 64 | 229 | 21.4
Code Review |  | 38 | 5 | 140 | 13
Compile |  | 0 | 0 | 0 | 0
Test |  | 36 | 36 | 162 | 15.1
Postmortem |  | 10 | 0 | 36 | 3.3
Total |  | 257 | 167 | 1073 | 100
UPI (70%)
LPI (70%)
PSP3 Project Plan Summary - Program
Student | RMM |  |  | Date | 2017-05-03
Program | Baja Maestros |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Defects Injected
Planning |  | 0 | 0 | 0 | 0
High-level Design |  | 0 | 0 | 0 | 0
HLDR |  | 0 | 0 | 0 | 0
Design |  | 3.8 | 0 | 11 | 52.4
Design Review |  | 0 | 0 | 0 | 0
Code |  | 3.1 | 1 | 10 | 47.6
Code Review |  | 0 | 0 | 0 | 0
Compile |  | 0 | 0 | 0 | 0
Test |  | 0 | 0 | 0 | 0
Total Development |  | 7 | 1 | 21 | 100
Defects Removed
Planning |  | 0 | 0 | 0 | 0
High-level Design |  | 0 | 0 | 0 | 0
HLDR |  | 0 | 0 | 0 | 0
Design |  | 0 | 0 | 0 | 0
Design Review |  | 3.5 | 0 | 10 | 47.6
Code |  | 0 | 0 | 0 | 0
Code Review |  | 2.8 | 0 | 8 | 38.1
Compile |  | 0 | 0 | 0 | 0
Test |  | 0.7 | 1 | 3 | 14.3
Total Development |  | 7 | 1 | 21 | 100
After Development |  |  | 0 | 0
Defect Removal Efficiency
Def/Hr - HLDR |  | 0 | 0 | 0
Def/Hr - DLDR |  | 8.92 | 0 | 6.7
Def/Hr - CDR |  | 4.36 | 0 | 3.44
Def/Hr - Compile |  | 0 | 0 | 0
Def/Hr - Test |  | 1.17 | 1.68 | 1.11
DRL(HLDR/UT) |  | 0 | 0 | 0
DRL(DLDR/UT) |  | 7.62 | 0 | 6.01
DRL(CDR/UT) |  | 3.73 | 0 | 3.08
DRL(Compile/UT) |  | 0 | 0 | 0

## Size estimated template
Size Estimating Template
Student | RMM |  |  |  | Date |  | 2017-05-03
Instructor | PEBM |  |  |  | Program# |  | N/A
BASE PROGRAM LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE SIZE (B) => |  |  |  |  | 23 |  | 0
LOC DELETED (D) => |  |  |  |  | 2 |  | 0
LOC MODIFIED (M) => |  |  |  |  | 5 |  | 0
OBJECT LOC
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC |  | C++ Object Size in LOC per Method
[9 empty] | Category | VS | S | M | L | VL
[9 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[9 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[9 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[9 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
(BA) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
TOTAL BASE ADDITIONS (BA) |  |  |  |  | 0 |  | 0 |  | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
query_maestros |  | logic | 1 | L | 23.3 |  | 43
delate_maestros |  | logic | 1 | M | 16 |  | 22
delate_imparte |  | logic | 1 | M |  |  | 22
int_main |  | logic | 1 | VS | 7.6 |  | 8
baja_maestros |  | logic | 1 | VL | 77.7 |  | 61
(NO) subtotal from page 2 |  |  |  |  | 0 |  | 0
TOTAL NEW OBJECTS (NO) |  |  |  |  | 124.4 |  | 156
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
(R) subtotal from page 2 |  |  |  |  | 0 |  | 0
REUSED TOTAL (R) |  |  |  |  | 0 |  | 0
[5 empty] | Size |  | Time
Estimated Object LOC: |  |  | E = BA+NO+M |  | 129.42
Regression Parameter: |  |  | B0 |  | 18.49 |  | 0
Regression Parameter: |  |  | B1 |  | 0.67 |  | 1.98
Estimated New and Changed LOC: |  |  | N = B0 + B1` * E |  | 105.4
Estimated Total LOC: |  |  | T = N + B - D - M + R |  | 121.4
Estimated Total New Reuse (sum of * LOC): |  |  |  |  | 0
Estimated Total Developent Time: |  |  | Time = B0 + B1` * E |  |  |  | 256.9
Prediction Range: |  |  | Range |  | 21.2 |  | 0
Upper Prediction Interval: |  |  | UPI = N + Range |  | 126.6
Lower Prediction Interval: |  |  | LPI = N - Range |  | 84.3
Prediction Interval Percent |  |  |  |  | 70% |  | 70%
Method Selected |  |  |  |  | A |  | C
R^2 |  |  |  |  | 0.88 |  | 0
Size Estimating Template (continued)
Student | RMM |  |  |  | Date |  | 2017-05-03
Instructor | PEBM |  |  |  | Program# |  | N/A
OBJECT LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC
C++ Object Size in LOC per Method
[15 empty] | Category | VS | S | M | L | VL
[15 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[15 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[15 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[15 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
[15 empty] | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
[15 empty] | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
SUBTOTAL BASE ADDITIONS (BA) => |  |  |  |  | 0 |  | 0
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
SUBTOTAL NEW OBJECTS (NO) => |  |  |  |  | 0 |  | 0
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
SUBTOTAL REUSED (R) => |  |  |  |  | 0 |  | 0

## Task Planning Template
| Project | Baja Maestros |  |  |  | Instructor | PEBM
Task |  | Plan |  |  |  |  | Actual
Number | Name | Minutes | Planned Value | Cumulative Minutes | Cumulative Planned Value | Date Monday | Date | Earned Value | Cumulative Earned Value
1 | Planning | 45 | 17.51% | 45 | 17.51% | 2017-05-01 | 2017-05-01 | 17.51% | 17.51%
2 | High-level Design | 0 | 0% | 45 | 17.51% | 2017-05-01 | 2017-05-01 | 0% | 17.51%
3 | HLDR | 0 | 0% | 45 | 17.51% | 2017-05-01 | 2017-05-01 | 0% | 17.51%
4 | Design | 57 | 22.18% | 102 | 39.69% | 2017-05-01 | 2017-05-01 | 22.18% | 39.69%
5 | Design Review | 23 | 8.949% | 125 | 48.64% | 2017-05-01 | 2017-05-01 | 8.949% | 48.64%
6 | Code | 47 | 18.29% | 172 | 66.93% | 2017-05-02 | 2017-05-04 | 18.29% | 66.93%
7 | Code Review | 38 | 14.79% | 210 | 81.71% | 2017-05-02 | 2017-05-08 | 14.79% | 81.71%
8 | Compile | 0 | 0% | 210 | 81.71% | 2017-05-02 | 2017-05-08 | 0% | 81.71%
9 | Test | 36 | 14.01% | 246 | 95.72% | 2017-05-02 | 2017-05-08 | 14.01% | 95.72%
10 | Postmortem | 10 | 3.891% | 256 | 99.61% | 2017-05-02 | 2017-05-08 | 3.891% | 99.61%
| Total | 257 | 100%

## Schedule Planning Template
Table C49 Schedule Planning Template
| Student | RMM |  |  |  | Date | 2017-05-03
| Project | Baja Maestros |  |  |  | Instructor | PEBM
|  | Plan |  |  | Actual
Day Number | Date Monday | Direct Min | Cumutative Minute | Cumulative Planned Value | Direct Min | Cumulative Minutes | Cumulative Earned Value
4 | 2017-05-01 | 45 | 45 | 17.51% | 20 | 20 | 17.51%
4 | 2017-05-01 | 0 | 45 | 17.51% | 6 | 26 | 17.51%
4 | 2017-05-01 | 0 | 45 | 17.51% | 2 | 28 | 17.51%
4 | 2017-05-01 | 57 | 102 | 39.69% | 28 | 56 | 39.69%
4 | 2017-05-01 | 23 | 125 | 48.64% | 7 | 63 | 48.64%
|  | 47 | 172 | 66.93% | 64 | 127 | 66.93%
|  | 38 | 210 | 81.71% | 5 | 132 | 81.71%
|  | 0 | 210 | 81.71% | 0 | 132 | 81.71%
|  | 36 | 246 | 95.72% | 36 | 168 | 95.72%
|  | 10 | 256 | 99.61% | 0 | 168 | 99.61%