## Project Plan Summary
PSP3 Project Plan Summary
Student | JAGC |  |  | Date | 2017-04-21
Program | Cambios Alumnos |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Summary
LOC/Hour |  | 20.93 | 21.05 | 24.01
Planned Time |  | 283 |  | 1650
Actual Time |  |  | 379 | 2682
CPI (Planned/Actual Time) |  |  |  | 0.62
% Reused |  | 22.4 | 15.6 | 15.5
% New Reused |  | 0 | 0 | 0
Test Defects/KLOC |  | 4.95 | 0 | 4.06
Total Defects/KLOC |  | 54.46 | 0 | 44.65
Yield % |  | 87.9 | 100 | 87.9
% Appraisal COQ |  | 12.3 | 17.7 | 13.4
% Failure COQ |  | 6.1 | 9.5 | 6.8
COQ A/F Ratio |  | 2.01 | 1.85 | 1.96
Program Size (LOC)
Base(B) |  | 16 | 30
Deleted(D) |  | 2 | 0
Modified(M) |  | 5 | 1
Added(A) |  | 94 | 132
Reused(R) |  | 31 | 30 | 148
Total N&C (N) |  | 99 | 133 | 739
Total LOC(T) |  | 139 | 192 | 952
Total New Reused |  | 0 | 0 | 0
Total Object LOC(E) |  | 98.64 | 158 | 691
UPI (70%)
LPI (70%)
Time in Phase (min.)
Planning |  | 55 | 83 | 370 | 20
High-level Design |  | 0 | 25 | 25 | 1.4
HLDR |  | 0 | 11 | 11 | 0.6
Design |  | 129 | 95 | 762 | 41.3
Design Review |  | 17 | 33 | 124 | 6.7
Code |  | 39 | 62 | 266 | 14.4
Code Review |  | 17 | 34 | 123 | 6.7
Compile |  | 2 | 0 | 12 | 0.7
Test |  | 15 | 36 | 113 | 6.1
Postmortem |  | 8 | 0 | 41 | 2.2
Total |  | 283 | 379 | 1847 | 100
UPI (70%) |  | 599
LPI (70%) |  | 0
PSP3 Project Plan Summary
Student | JAGC |  |  | Date | 2017-04-21
Program | Cambios Alumnos |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Defects Injected
Planning |  | 0.2 | 0 | 1 | 3
High-level Design |  | 0 | 0 | 0 | 0
HLDR |  | 0 | 0 | 0 | 0
Design |  | 3.4 | 0 | 21 | 63.6
Design Review |  | 0 | 0 | 0 | 0
Code |  | 1.8 | 0 | 11 | 33.3
Code Review |  | 0 | 0 | 0 | 0
Compile |  | 0 | 0 | 0 | 0
Test |  | 0 | 0 | 0 | 0
Total Development |  | 5.4 | 0 | 33 | 100
Defects Removed
Planning |  | 0 | 0 | 0 | 0
High-level Design |  | 0 | 0 | 0 | 0
HLDR |  | 0 | 0 | 0 | 0
Design |  | 0.3 | 0 | 2 | 6.1
Design Review |  | 2.3 | 0 | 14 | 42.4
Code |  | 1 | 0 | 6 | 18.2
Code Review |  | 1.1 | 0 | 7 | 21.2
Compile |  | 0.2 | 0 | 1 | 3
Test |  | 0.5 | 0 | 3 | 9.1
Total Development |  | 5.4 | 0 | 33 | 100
After Development |  |  | 0 | 0
Defect Removal Efficiency
Def/Hr - HLDR |  | 0 | 0 | 0
Def/Hr - DLDR |  | 7.82 | 0 | 6.79
Def/Hr - CDR |  | 3.98 | 0 | 3.41
Def/Hr - Compile |  | 4.18 | 0 | 4.88
Def/Hr - Test |  | 1.97 | 0 | 1.59
DRL(HLDR/UT) |  | 0 | 0 | 0
DRL(DLDR/UT) |  | 3.98 | 0 | 4.28
DRL(CDR/UT) |  | 2.02 | 0 | 2.15
DRL(Compile/UT) |  | 2.13 | 0 | 3.08

## Size estimated template
Size Estimating Template
Student | JAGC |  |  |  | Date |  | 2017-04-21
Instructor | PEBM |  |  |  | Program# |  | Cambios Alumnos
BASE PROGRAM LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE SIZE (B) => |  |  |  |  | 16 |  | 30
LOC DELETED (D) => |  |  |  |  | 2 |  | 0
LOC MODIFIED (M) => |  |  |  |  | 5 |  | 1
OBJECT LOC
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC |  | C++ Object Size in LOC per Method
[9 empty] | Category | VS | S | M | L | VL
[9 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[9 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[9 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[9 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
(BA) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
TOTAL BASE ADDITIONS (BA) |  |  |  |  | 0 |  | 0 |  | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
cambios_alumnos() |  | Text | 1 | VL | 77.7 |  | 96
update_alumnos() |  | Logic | 1 | M | 16 |  | 61
(NO) subtotal from page 2 |  |  |  |  | 0 |  | 0
TOTAL NEW OBJECTS (NO) |  |  |  |  | 93.6 |  | 157
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
query_alumnos() |  |  |  |  | 31 |  | 30
(R) subtotal from page 2 |  |  |  |  | 0 |  | 0
REUSED TOTAL (R) |  |  |  |  | 31 |  | 30
[5 empty] | Size |  | Time
Estimated Object LOC: |  |  | E = BA+NO+M |  | 98.64
Regression Parameter: |  |  | B0 |  | 0 |  | 43.99
Regression Parameter: |  |  | B1 |  | 1 |  | 2.42
Estimated New and Changed LOC: |  |  | N = B0 + B1` * E |  | 98.6
Estimated Total LOC: |  |  | T = N + B - D - M + R |  | 138.6
Estimated Total New Reuse (sum of * LOC): |  |  |  |  | 0
Estimated Total Developent Time: |  |  | Time = B0 + B1` * E |  |  |  | 282.8
Prediction Range: |  |  | Range |  | 0 |  | 315.9
Upper Prediction Interval: |  |  | UPI = N + Range |  |  |  | 598.7
Lower Prediction Interval: |  |  | LPI = N - Range |  |  |  | 0
Prediction Interval Percent |  |  |  |  | 70% |  | 70%
Method Selected |  |  |  |  | D |  | A
R^2 |  |  |  |  | 0 |  | 0.21
Size Estimating Template (continued)
Student | JAGC |  |  |  | Date |  | 2017-04-21
Instructor | PEBM |  |  |  | Program# |  | Cambios Alumnos
OBJECT LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC
C++ Object Size in LOC per Method
[15 empty] | Category | VS | S | M | L | VL
[15 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[15 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[15 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[15 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
[15 empty] | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
[15 empty] | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
SUBTOTAL BASE ADDITIONS (BA) => |  |  |  |  | 0 |  | 0
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
SUBTOTAL NEW OBJECTS (NO) => |  |  |  |  | 0 |  | 0
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
SUBTOTAL REUSED (R) => |  |  |  |  | 0 |  | 0

## Task Planning Template
| Project | Cambios Alumnos |  |  |  | Instructor | PEBM
Task |  | Plan |  |  |  |  | Actual
Number | Name | Minutes | Planned Value | Cumulative Minutes | Cumulative Planned Value | Date Monday | Date | Earned Value | Cumulative Earned Value
1 | Planning | 55 | 19.43% | 55 | 19.43% | 2017-04-21 | 2017-04-20 | 19.43% | 19.43%
2 | High-level Design | 0 | 0% | 55 | 19.43% | 2017-04-21 | 2017-05-01 | 0% | 19.43%
3 | HLDR | 0 | 0% | 55 | 19.43% | 2017-04-21 | 2017-05-01 | 0% | 19.43%
4 | Design | 129 | 45.58% | 184 | 65.02% | 2017-04-24 | 2017-05-01 | 45.58% | 65.02%
5 | Design Review | 17 | 6.007% | 201 | 71.02% | 2017-04-24 | 2017-05-01 | 6.007% | 71.02%
6 | Code | 39 | 13.78% | 240 | 84.81% | 2017-04-25 | 2017-05-02 | 13.78% | 84.81%
7 | Code Review | 17 | 6.007% | 257 | 90.81% | 2017-04-25 | 2017-05-02 | 6.007% | 90.81%
8 | Compile | 2 | 0.7067% | 259 | 91.52% | 2017-04-26 | 2017-05-02 | 0.7067% | 91.52%
9 | Test | 15 | 5.3% | 274 | 96.82% | 2017-04-26 | 2017-05-07 | 5.3% | 96.82%
10 | Postmortem | 8 | 2.827% | 282 | 99.65% | 2017-04-26 | 2017-05-07 | 2.827% | 99.65%
| Total | 283 | 100%

## Schedule Planning Template
Table C49 Schedule Planning Template
| Student | JAGC |  |  |  | Date | 2017-04-21
| Project | Cambios Alumnos |  |  |  | Instructor | PEBM
|  | Plan |  |  | Actual
Day Number | Date Monday | Direct Min | Cumutative Minute | Cumulative Planned Value | Direct Min | Cumulative Minutes | Cumulative Earned Value | Adjusted Earned Value
1 | 2017-04-21 | 55 | 55 | 19.5% | 83 | 83 | 19.5% | 20.73%
2 | 2017-04-22 | 0 | 55 | 19.5% | 0 | 83 | 19.5% | 20.73%
3 | 2017-04-23 | 0 | 55 | 19.5% | 0 | 83 | 19.5% | 20.73%
4 | 2017-04-24 | 146 | 201 | 71.28% | 0 | 83 | 20% | 20.73%
5 | 2017-04-25 | 56 | 257 | 91.13% | 0 | 83 | 20% | 20.73%
6 | 2017-04-26 | 25 | 282 | 100% | 0 | 83 | 20% | 20.73%
7 | 2017-05-01 |  |  |  | 164 | 247 | 71.28% | 61.69%
8 | 2017-05-02 |  |  |  | 96.2 | 343.2 | 91.13% | 85.71%
9 | 2017-05-07 |  |  |  | 57.2 | 400.4 | 100% | 100%