## Summary
PSP3 Project Plan Summary - Cambios Maestros
Student | GVV |  |  | Date | 26/04/17
Program | Cambios Maestros |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Summary
LOC/Hour |  | 37.61 | 35.58 | 32.62
Planned Time |  | 245 |  | 1158
Actual Time |  |  | 420 | 1502
CPI (Planned/Actual Time) |  |  |  | 0.77
% Reused |  | 0 | 0 | 0
% New Reused |  | 0 | 0 | 0
Test Defects/KLOC |  | 0 | 4.02 | 2.27
Total Defects/KLOC |  | 171.88 | 4.02 | 77.1
Yield % |  | 84.8 | 0 | 82.4
% Appraisal COQ |  | 10.5 | 2.6 | 6.4
% Failure COQ |  | 6.9 | 17.6 | 12.4
COQ A/F Ratio |  | 1.53 | 0.15 | 0.52
Program Size (LOC)
Base(B) |  | 100 | 53
Deleted(D) |  | 25 | 0
Modified(M) |  | 30 | 11
Added(A) |  | 124 | 238
Reused(R) |  | 0 | 0 | 0
Total N&C (N) |  | 154 | 249 | 441
Total LOC(T) |  | 199 | 291 | 727
Total New Reused |  | 0 | 0 | 0
Total Object LOC(E) |  | 147.64 | 291 | 478
UPI (70%)
LPI (70%)
Time in Phase (min.)
Planning |  | 63 | 45 | 146 | 18
High-level Design |  | 0 | 0 | 0 | 0
HLDR |  | 0 | 0 | 0 | 0
Design |  | 74 | 104 | 222 | 27.4
Design Review |  | 12 | 4 | 24 | 2.9
Code |  | 50 | 168 | 247 | 30.4
Code Review |  | 13 | 7 | 28 | 3.5
Compile |  | 1 | 0 | 2 | 0.2
Test |  | 16 | 74 | 99 | 12.2
Postmortem |  | 16 | 18 | 43 | 5.3
Total |  | 245 | 420 | 811 | 100
UPI (70%)
LPI (70%)
PSP3 Project Plan Summary - Cambios Maestros
Student | GVV |  |  | Date | 26/04/17
Program | Cambios Maestros |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Defects Injected
Planning |  | 3.2 | 0 | 4 | 11.8
High-level Design |  | 0 | 0 | 0 | 0
HLDR |  | 0 | 0 | 0 | 0
Design |  | 16.8 | 0 | 21 | 61.8
Design Review |  | 0 | 0 | 0 | 0
Code |  | 6.4 | 1 | 9 | 26.5
Code Review |  | 0 | 0 | 0 | 0
Compile |  | 0 | 0 | 0 | 0
Test |  | 0 | 0 | 0 | 0
Total Development |  | 26.4 | 1 | 34 | 100
Defects Removed
Planning |  | 0 | 0 | 0 | 0
High-level Design |  | 0 | 0 | 0 | 0
HLDR |  | 0 | 0 | 0 | 0
Design |  | 0 | 0 | 0 | 0
Design Review |  | 16.8 | 0 | 21 | 61.8
Code |  | 0 | 0 | 0 | 0
Code Review |  | 5.6 | 0 | 7 | 20.6
Compile |  | 4 | 0 | 5 | 14.7
Test |  | 0 | 1 | 1 | 2.9
Total Development |  | 26.4 | 1 | 34 | 100
After Development |  |  | 0 | 0
Defect Removal Efficiency
Def/Hr - HLDR |  | 0 | 0 | 0
Def/Hr - DLDR |  | 80.67 | 0 | 52.76
Def/Hr - CDR |  | 25.38 | 0 | 14.85
Def/Hr - Compile |  | 218.97 | 0 | 165.14
Def/Hr - Test |  | 0 | 0.81 | 0.61
DRL(HLDR/UT) |  | 0 | 0 | 0
DRL(DLDR/UT) |  | 0 | 0 | 87.06
DRL(CDR/UT) |  | 0 | 0 | 24.5
DRL(Compile/UT) |  | 0 | 0 | 272.5

## Size Estimating Template
Size Estimating Template
Student | Guillermo Vivaldo Vazquez | GVV |  |  | Date |  | 26/04/17
Instructor | Patricia Erendira Benavides Muratalla | PEBM |  |  | Program# |  | N/A
BASE PROGRAM LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE SIZE (B) => |  |  |  |  | 100 |  | 53
LOC DELETED (D) => |  |  |  |  | 25 |  | 0
LOC MODIFIED (M) => |  |  |  |  | 30 |  | 11
OBJECT LOC
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC
static int_callback |  | I/O | 1 | VS | 9 |  | 9 |  | C++ Object Size in LOC per Method
insert_mtr_plan |  | I/O | 1 | L | 21.6 |  | 0 |  | Category | VS | S | M | L | VL
insrt_mtr |  | I/O | 1 | L | 21.6 |  | 0 |  | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
query_maestros |  | I/O | 1 | VL | 28.9 |  | 44 |  | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[9 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
(BA) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
TOTAL BASE ADDITIONS (BA) |  |  |  |  | 81.2 |  | 53 |  | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | * | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
cambios_maestros |  | I/O | 1 | VL | 28.9 |  | 131
int_main() |  | Logic | 1 | VS | 7.6 |  | 8
update_maestros |  | I/O | 1 |  |  |  | 57
update_imparte |  | I/O | 1 |  |  |  | 31
(NO) subtotal from page 2 |  |  |  |  | 0 |  | 0
TOTAL NEW OBJECTS (NO) |  |  |  |  | 36.5 |  | 227
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
(R) subtotal from page 2 |  |  |  |  | 0 |  | 0
REUSED TOTAL (R) |  |  |  |  | 0 |  | 0
[5 empty] | Size |  | Time
Estimated Object LOC: |  |  | E = BA+NO+M |  | 147.64
Regression Parameter: |  |  | B0 |  | 0 |  | 0
Regression Parameter: |  |  | B1 |  | 1.04 |  | 1.66
Estimated New and Changed LOC: |  |  | N = B0 + B1` * E |  | 153.5
Estimated Total LOC: |  |  | T = N + B - D - M + R |  | 198.5
Estimated Total New Reuse (sum of * LOC): |  |  |  |  | 0
Estimated Total Developent Time: |  |  | Time = B0 + B1` * E |  |  |  | 244.9
Prediction Range: |  |  | Range |  | 0 |  | 0
Upper Prediction Interval: |  |  | UPI = N + Range
Lower Prediction Interval: |  |  | LPI = N - Range
Prediction Interval Percent |  |  |  |  | 70% |  | 70%
Method Selected |  |  |  |  | C |  | C
R^2 |  |  |  |  | 0 |  | 0
Size Estimating Template (continued)
Student | Guillermo Vivaldo Vazquez |  |  |  | Date |  | ?????
Instructor | Jorge Rafael Aguilar Cisneros |  |  |  | Program# |  | #######
OBJECT LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC
C++ Object Size in LOC per Method
[9 empty] | Category | VS | S | M | L | VL
[9 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[9 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[9 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[9 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
[9 empty] | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
[9 empty] | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
*
SUBTOTAL NEW OBJECTS (NO) => |  |  |  |  | 0 |  | 101
SUBTOTAL NEW OBJECTS (NO) => |  |  |  |  | 0 |  | 0
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
SUBTOTAL REUSED (R) => |  |  |  |  | 0 |  | 0

## TaskPlanning
| Project | Cambios-Maestros |  |  |  | Instructor | PEBM
Task |  | Plan |  |  |  |  | Actual
Number | Name | Minutes | Planned Value | Cumulative Minutes | Cumulative Planned Value | Date Monday | Date | Earned Value | Cumulative Earned Value
1 | Planning | 63 | 20% | 63 | 20% | 2017-04-26 | 2017-04-29 | 20% | 20%
2 | High-level Design | 0 | 0% | 63 | 20% | 2017-04-26 | 2017-04-30 | 0% | 20%
3 | HLDR | 0 | 0% | 63 | 20% | 2017-04-26 | 2017-04-30 | 0% | 20%
4 | Design | 74 | 46% | 137 | 66% | 2017-04-28 | 2017-04-30 | 46% | 66%
5 | Design Review | 12 | 6% | 149 | 72% | 2017-04-28 | 2017-04-30 | 6% | 72%
6 | Code | 50 | 14% | 199 | 86% | 2017-04-29 | 2017-05-03 | 14% | 86%
7 | Code Review | 13 | 6% | 212 | 92% | 2017-04-29 | 2017-05-03 | 6% | 92%
8 | Compile | 1 | 1% | 213 | 93% | 2017-04-29 | 2017-05-04 | 1% | 93%
9 | Test | 16 | 5% | 229 | 98% | 2017-04-30 | 2017-05-06 | 5% | 98%
10 | Postmortem | 16 | 2% | 245 | 100% | 2017-04-30 | 2017-05-06 | 2% | 100%
| Total | 245 | 100%

## SchedulePlanning
Table C49 Schedule Planning Template
| Student | GVV |  |  |  | Date | 26/04/17
| Project | Cambios Maestros |  |  |  | Instructor | PEBM
|  | Plan |  |  | Actual
Day Number | Date Monday | Direct Min | Cumutative Minute | Cumulative Planned Value | Direct Min | Cumulative Minutes | Cumulative Earned Value | Adjusted Earned Value
1 | 2017-04-26 | 63 | 63 | 20% | 21.6 | 21.6 | 20% | 4.985%
2 | 2017-04-28 | 86 | 149 | 72% | 0 | 21.6 | 20% | 4.985%
3 | 2017-04-29 | 64 | 213 | 93% | 22.2 | 43.8 | 20% | 10.11%
4 | 2017-04-30 | 32 | 245 | 100% | 122.3 | 166.1 | 72% | 38.33%
5 | 2017-05-03 | 0 | 0 | 100% | 175 | 341.1 | 92% | 78.72%
6 | 2017-05-04 | 0 | 0 | 100% | 0.1 | 341.2 | 93% | 78.74%
7 | 2017-05-05 | 0 | 0 | 100% | 25.9 | 367.1 | 93% | 84.72%
8 | 2017-05-06 | 0 | 0 | 100% | 66.2 | 433.3 | 100% | 100%