## Project Plan Summary
PSP3 Project Plan Summary
Student | BRA |  |  | Date | 2017-04-26
Program | Cambios Planes |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Summary
LOC/Hour |  | 26.69
Planned Time |  | 228
Actual Time
CPI (Planned/Actual Time)
% Reused |  | 0
% New Reused |  | 0
Test Defects/KLOC |  | 2.92
Total Defects/KLOC |  | 26.24
Yield % |  | 88.9
% Appraisal COQ |  | 7.2
% Failure COQ |  | 5.7
COQ A/F Ratio |  | 1.28
Program Size (LOC)
Base(B) |  | 0 | 0
Deleted(D) |  | 0 | 0
Modified(M) |  | 0 | 0
Added(A) |  | 102 | 95
Reused(R) |  | 0 | 19
Total N&C (N) |  | 102 | 95
Total LOC(T) |  | 102 | 114
Total New Reused |  | 0 | 0
Total Object LOC(E) |  | 127.49 | 95
UPI (70%) |  | 155
LPI (70%) |  | 49
Time in Phase (min.)
Planning |  | 44
High-level Design |  | 42
HLDR |  | 16
Design |  | 54
Design Review |  | 12
Code |  | 29
Code Review |  | 9
Compile |  | 0
Test |  | 2
Postmortem |  | 20
Total |  | 228
UPI (70%) |  | 299
LPI (70%) |  | 158
Student | BRA |  |  | Date | 2017-04-26
Program | Cambios Planes |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Defects Injected
Planning |  | 0.9
High-level Design |  | 0
HLDR |  | 0
Design |  | 0.3
Design Review |  | 0
Code |  | 1.5
Code Review |  | 0
Compile |  | 0
Test |  | 0
Total Development |  | 2.7
Defects Removed
Planning |  | 0.6
High-level Design |  | 0
HLDR |  | 0
Design |  | 0.3
Design Review |  | 0.3
Code |  | 0
Code Review |  | 1.2
Compile |  | 0
Test |  | 0.3
Total Development |  | 2.7
After Development
Defect Removal Efficiency
Def/Hr - HLDR |  | 0
Def/Hr - DLDR |  | 2.24
Def/Hr - CDR |  | 8.3
Def/Hr - Compile |  | 0
Def/Hr - Test |  | 1.49
DRL(HLDR/UT) |  | 0
DRL(DLDR/UT) |  | 1.51
DRL(CDR/UT) |  | 5.58
DRL(Compile/UT) |  | 0

## Size estimated template
Size Estimating Template
Student | BRA |  |  |  | Date |  | 2017-04-26
Instructor | PEBM |  |  |  | Program# |  | Cambios Planes
BASE PROGRAM LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE SIZE (B) => |  |  |  |  | 0 |  | 0
LOC DELETED (D) => |  |  |  |  | 0 |  | 0
LOC MODIFIED (M) => |  |  |  |  | 0 |  | 0
OBJECT LOC
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC |  | C++ Object Size in LOC per Method
[9 empty] | Category | VS | S | M | L | VL
[9 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[9 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[9 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[9 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
(BA) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
TOTAL BASE ADDITIONS (BA) |  |  |  |  | 0 |  | 0 |  | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
cambios_planes() |  | Text | 1 | VL | 77.7 |  | 60
update_planes() |  | Logic | 1 | M | 16 |  | 28
int main() | [6 empty] | 7
(NO) subtotal from page 2 |  |  |  |  | 0 |  | 0
TOTAL NEW OBJECTS (NO) |  |  |  |  | 93.7 |  | 95
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
query_planes() |  |  |  |  | 31 |  | 19
(R) subtotal from page 2 |  |  |  |  | 0 |  | 0
REUSED TOTAL (R) |  |  |  |  | 31 |  | 19
[5 empty] | Size |  | Time
Estimated Object LOC: |  |  | E = BA+NO+M |  | 93.7
Regression Parameter: |  |  | B0 |  | 0 |  | 0
Regression Parameter: |  |  | B1 |  | 1.2 |  | 2.26
Estimated New and Changed LOC: |  |  | N = B0 + B1` * E |  | 112.44
Estimated Total LOC: |  |  | T = N + B - D - M + R |  | 143.44
Estimated Total New Reuse (sum of * LOC): |  |  |  |  | 0
Estimated Total Developent Time: |  |  | Time = B0 + B1` * E |  |  |  | 81
Prediction Range: |  |  | Range |  | 0 |  | 0
Upper Prediction Interval: |  |  | UPI = N + Range |  | 0 |  | 0
Lower Prediction Interval: |  |  | LPI = N - Range |  | 0 |  | 0
Prediction Interval Percent |  |  |  |  | 70% |  | 70%
Method Selected |  |  |  |  | C |  | C
R^2 |  |  |  |  | 0 |  | 0
Size Estimating Template (continued)
Student | BRA |  |  |  | Date |  | 2017-04-26
Instructor | PEBM |  |  |  | Program# |  | Cambios Planes
OBJECT LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC
C++ Object Size in LOC per Method
[15 empty] | Category | VS | S | M | L | VL
[15 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[15 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[15 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[15 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
[15 empty] | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
[15 empty] | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
SUBTOTAL BASE ADDITIONS (BA) => |  |  |  |  | 0 |  | 0
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
SUBTOTAL NEW OBJECTS (NO) => |  |  |  |  | 0 |  | 0
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
SUBTOTAL REUSED (R) => |  |  |  |  | 0 |  | 0

## Task Planning Template
| Project | Cambios Planes |  |  |  | Instructor | PEBM
Task |  | Plan |  |  |  |  | Actual
Number | Name | Minutes | Planned Value | Cumulative Minutes | Cumulative Planned Value | Date Monday | Date | Earned Value | Cumulative Earned Value
1 | Planning | 44 | 19.3% | 44 | 19.3% | 2017-04-22 | 2017-04-26 | 19.3% | 19.3%
2 | High-level Design | 42 | 18.42% | 86 | 37.72% | 2017-04-28 |  | 18.42% | 37.72%
3 | HLDR | 16 | 7.018% | 102 | 44.74% | 2017-04-28 |  | 7.018% | 44.74%
4 | Design | 54 | 23.68% | 156 | 68.42% | 2017-04-29 |  | 23.68% | 68.42%
5 | Design Review | 12 | 5.263% | 168 | 73.68% | 2017-04-29 |  | 5.263% | 73.68%
6 | Code | 29 | 12.72% | 197 | 86.4% | 2017-04-30 |  | 12.72% | 86.4%
7 | Code Review | 9 | 3.947% | 206 | 90.35% | 2017-04-30 |  | 3.947% | 90.35%
8 | Compile | 0 | 0% | 206 | 90.35% | 2017-04-30 |  | 0% | 90.35%
9 | Test | 2 | 0.8772% | 208 | 91.23% | 2017-05-01 |  | 0.8772% | 91.23%
10 | Postmortem | 20 | 8.772% | 228 | 100% | 2017-05-01 |  | 8.772% | 100%
| Total | 228 | 100%

## Schedule Planning Template
Table C49 Schedule Planning Template
| Student | BRA |  |  |  | Date | 2017-04-26
| Project | Cambios Planes |  |  |  | Instructor | PEBM
|  | Plan |  |  | Actual
Day Number | Date Monday | Direct Min | Cumutative Minute | Cumulative Planned Value | Direct Min | Cumulative Minutes | Cumulative Earned Value | Adjusted Earned Value
1 | 2017-04-22 | 44 | 44 | 19.3%
2 | 2017-04-28 | 58 | 102 | 44.74%
3 | 2017-04-29 | 66 | 168 | 73.68%
4 | 2017-04-30 | 38 | 206 | 90.35%
5 | 2017-04-01 | 22 | 228 | 100%