## Project Plan Summary
PSP3 Project Plan Summary
Student | JAGC |  |  | Date | 2017-04-21
Program | Menú Reportes Alumnos |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Summary
LOC/Hour |  | 8.87 | 14.43 | 22.37
Planned Time |  | 280 |  | 1647
Actual Time |  |  | 237 | 2613
CPI (Planned/Actual Time) |  |  |  | 0.63
% Reused |  | 0 | 0 | 14.4
% New Reused |  | 0 | 0 | 0
Test Defects/KLOC |  | 4.95 | 0 | 4.52
Total Defects/KLOC |  | 54.46 | 175.44 | 64.86
Yield % |  | 87.9 | 100 | 90.7
% Appraisal COQ |  | 12.3 | 15.2 | 12.1
% Failure COQ |  | 6.1 | 3 | 5.4
COQ A/F Ratio |  | 2.01 | 5.14 | 2.24
Program Size (LOC)
Base(B) |  | 16 | 9
Deleted(D) |  | 2 | 1
Modified(M) |  | 5 | 3
Added(A) |  | 36 | 54
Reused(R) |  | 0 | 0 | 118
Total N&C (N) |  | 41 | 57 | 663
Total LOC(T) |  | 50 | 62 | 822
Total New Reused |  | 0 | 0 | 0
Total Object LOC(E) |  | 41.41 | 56 | 589
UPI (70%)
LPI (70%)
Time in Phase (min.)
Planning |  | 55 | 62 | 349 | 19.6
High-level Design |  | 0 | 18 | 18 | 1
HLDR |  | 0 | 10 | 10 | 0.6
Design |  | 127 | 49 | 716 | 40.3
Design Review |  | 17 | 20 | 111 | 6.2
Code |  | 39 | 26 | 230 | 12.9
Code Review |  | 17 | 16 | 105 | 5.9
Compile |  | 2 | 0 | 12 | 0.7
Test |  | 15 | 7 | 84 | 4.7
Postmortem |  | 8 | 29 | 143 | 8
Total |  | 280 | 237 | 1778 | 100
UPI (70%) |  | 591
LPI (70%) |  | 0
Student | JAGC |  |  | Date | 2017-04-21
Program | Menú Reportes Alumnos |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Defects Injected
Planning |  | 0.1 | 3 | 4 | 9.3
High-level Design |  | 0 | 1 | 1 | 2.3
HLDR |  | 0 | 1 | 1 | 2.3
Design |  | 1.4 | 5 | 26 | 60.5
Design Review |  | 0 | 0 | 0 | 0
Code |  | 0.8 | 0 | 11 | 25.6
Code Review |  | 0 | 0 | 0 | 0
Compile |  | 0 | 0 | 0 | 0
Test |  | 0 | 0 | 0 | 0
Total Development |  | 2.3 | 10 | 43 | 100
Defects Removed
Planning |  | 0 | 0 | 0 | 0
High-level Design |  | 0 | 0 | 0 | 0
HLDR |  | 0 | 1 | 1 | 2.3
Design |  | 0.1 | 0 | 2 | 4.7
Design Review |  | 1 | 1 | 15 | 34.9
Code |  | 0.4 | 0 | 6 | 14
Code Review |  | 0.5 | 8 | 15 | 34.9
Compile |  | 0.1 | 0 | 1 | 2.3
Test |  | 0.2 | 0 | 3 | 7
Total Development |  | 2.3 | 10 | 43 | 100
After Development |  |  | 10 | 43
Defect Removal Efficiency
Def/Hr - HLDR |  | 0 | 6 | 6
Def/Hr - DLDR |  | 3.32 | 3 | 8.13
Def/Hr - CDR |  | 1.69 | 30 | 8.56
Def/Hr - Compile |  | 1.77 | 0 | 4.95
Def/Hr - Test |  | 0.83 | 0 | 2.13
DRL(HLDR/UT) |  | 0 | 2.58 | 2.81
DRL(DLDR/UT) |  | 3.98 | 1.29 | 3.81
DRL(CDR/UT) |  | 2.02 | 12.89 | 4.01
DRL(Compile/UT) |  | 2.13 | 0 | 2.32

## Size estimated template
Size Estimating Template
Student | JAGC |  |  |  | Date |  | 21/04/17.
Instructor | PEBM |  |  |  | Program# |  | Menú Reportes Alumnos
BASE PROGRAM LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE SIZE (B) => |  |  |  |  | 16 |  | 9
LOC DELETED (D) => |  |  |  |  | 2 |  | 1
LOC MODIFIED (M) => |  |  |  |  | 5 |  | 3
OBJECT LOC
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC |  | C++ Object Size in LOC per Method
[9 empty] | Category | VS | S | M | L | VL
[9 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[9 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[9 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[9 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
(BA) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
TOTAL BASE ADDITIONS (BA) |  |  |  |  | 0 |  | 0 |  | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
menu_reportes_alumnos() |  | text | 1 | L | 36.4 |  | 53
(NO) subtotal from page 2 |  |  |  |  | 0 |  | 0
TOTAL NEW OBJECTS (NO) |  |  |  |  | 36.4 |  | 53
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
(R) subtotal from page 2 |  |  |  |  | 0 |  | 0
REUSED TOTAL (R) |  |  |  |  | 0 |  | 0
[5 empty] | Size |  | Time
Estimated Object LOC: |  |  | E = BA+NO+M |  | 41.4
Regression Parameter: |  |  | B0 |  | 0 |  | 282.49
Regression Parameter: |  |  | B1 |  | 1.2 |  | -0.06
Estimated New and Changed LOC: |  |  | N = B0 + B1` * E |  | 49.68
Estimated Total LOC: |  |  | T = N + B - D - M + R |  | 58.68
Estimated Total New Reuse (sum of * LOC): |  |  |  |  | 0
Estimated Total Developent Time: |  |  | Time = B0 + B1` * E |  |  |  | 280.1
Prediction Range: |  |  | Range |  | 0 |  | 311
Upper Prediction Interval: |  |  | UPI = N + Range |  | 0 |  | 591.1
Lower Prediction Interval: |  |  | LPI = N - Range |  | 0 |  | 0
Prediction Interval Percent |  |  |  |  | 70% |  | 70%
Method Selected |  |  |  |  | C |  | C
R^2 |  |  |  |  | 0 |  | 0
Size Estimating Template (continued)
Student | JAGC |  |  |  | Date |  | 21/04/17.
Instructor | PEBM |  |  |  | Program# |  | Menú Reportes Alumnos
OBJECT LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC
C++ Object Size in LOC per Method
[15 empty] | Category | VS | S | M | L | VL
[15 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[15 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[15 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[15 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
[15 empty] | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
[15 empty] | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
SUBTOTAL BASE ADDITIONS (BA) => |  |  |  |  | 0 |  | 0
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
SUBTOTAL NEW OBJECTS (NO) => |  |  |  |  | 0 |  | 0
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
SUBTOTAL REUSED (R) => |  |  |  |  | 0 |  | 0

## Task Planning Template
| Project | Menú Reportes Alumnos |  |  |  | Instructor | PEBM
Task |  | Plan |  |  |  |  | Actual
Number | Name | Minutes | Planned Value | Cumulative Minutes | Cumulative Planned Value | Date Monday | Date | Earned Value | Cumulative Earned Value
1 | Planning | 55 | 19.64% | 55 | 19.64% | 21/04/17 | 21/04/17 | 19.64% | 19.64%
2 | High-level Design | 0 | 0% | 55 | 19.64% | 21/04/17 | 24/04/17 | 0% | 19.64%
3 | HLDR | 0 | 0% | 55 | 19.64% | 21/04/17 | 24/04/17 | 0% | 19.64%
4 | Design | 127 | 45.36% | 182 | 65% | 28/04/17 | 25/04/17 | 45.36% | 65%
5 | Design Review | 17 | 6.071% | 199 | 71.07% | 28/04/17 | 25/04/17 | 6.071% | 71.07%
6 | Code | 39 | 13.93% | 238 | 85% | 29/04/17 | 26/04/17 | 13.93% | 85%
7 | Code Review | 17 | 6.071% | 255 | 91.07% | 29/04/17 | 26/04/17 | 6.071% | 91.07%
8 | Compile | 2 | 0.7143% | 257 | 91.79% | 30/04/17 | 27/04/17 | 0.7143% | 91.79%
9 | Test | 15 | 5.357% | 272 | 97.14% | 30/04/17 | 27/04/17 | 5.357% | 97.14%
10 | Postmortem | 8 | 2.857% | 280 | 100% | 30/04/17 | 27/04/17 | 2.857% | 100%
| Total | 280 | 100%

## Schedule Planning Template
Table C49 Schedule Planning Template
| Student | JAGC |  |  |  | Date | 21/04/17
| Project | Menú Reportes Alumnos |  |  |  | Instructor | PEBM
|  | Plan |  |  | Actual
Day Number | Date Monday | Direct Min | Cumutative Minute | Cumulative Planned Value | Direct Min | Cumulative Minutes | Cumulative Earned Value | Adjusted Earned Value
1 | 21/04/17 | 55 | 55 | 19.64% | 62 | 62 | 20% | -0.3571%
2 | 22/04/17 | 0 | 55 | 19.64% | 0 | 62 | 20% | -0.3571%
3 | 23/04/17 | 0 | 55 | 19.64% | 0 | 62 | 20% | -0.3571%
4 | 24/04/17 | 0 | 55 | 19.64% | 28 | 90 | 20% | -0.3571%
5 | 25/04/17 | 0 | 55 | 19.64% | 69 | 159 | 71% | -51.36%
6 | 26/04/17 | 0 | 55 | 19.64% | 42 | 201 | 91% | -71.36%
| 27/04/17 | 0 | 55 | 19.64% | 36 | 237 | 100% | -80.36%
| 28/04/17 | 144 | 199 | 71.07%
| 29/04/17 | 56 | 255 | 91.07%
| 30/04/17 | 25 | 280 | 100%