## Project Plan Summary
PSP3 Project Plan Summary - Program
Student | JAGB |  |  | Date | 2017-04-24
Program | Menú Reporte Maestros |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Summary
LOC/Hour |  | 29.95 | 2.1 | 19.73
Planned Time |  | 155 |  | 996
Actual Time |  |  | 143 | 1411
CPI (Planned/Actual Time) |  |  |  | 0.71
% Reused |  | 0 | 0 | 35.2
% New Reused |  | 0 | 140 | 2.7
Test Defects/KLOC |  | 7.81 | 0 | 7.66
Total Defects/KLOC |  | 148.44 | 600 | 157.09
Yield % |  | 81.6 | 100 | 82.9
% Appraisal COQ |  | 21.2 | 21 | 21.2
% Failure COQ |  | 10.3 | 7 | 9.7
COQ A/F Ratio |  | 2.05 | 3 | 2.18
Program Size (LOC)
Base(B) |  | 30 | 48
Deleted(D) |  | 8 | 0
Modified(M) |  | 10 | 3
Added(A) |  | 57 | 2
Reused(R) |  | 0 | 0 | 270
Total N&C (N) |  | 67 | 5 | 261
Total LOC(T) |  | 79 | 48 | 767
Total New Reused |  | 0 | 7 | 7
Total Object LOC(E) |  | 55 | 48 | 342
UPI (70%) |  | 93
LPI (70%) |  | 41
Time in Phase (min.)
Planning |  | 15 | 13 | 200 | 25.1
High-level Design |  | 5 | 5 | 0 | 0
HLDR |  | 5 | 5 | 0 | 0
Design |  | 35 | 33 | 164 | 20.6
Design Review |  | 20 | 20 | 93 | 11.7
Code |  | 20 | 18 | 103 | 12.9
Code Review |  | 10 | 8 | 73 | 9.1
Compile |  | 5 | 3 | 18 | 2.2
Test |  | 15 | 7 | 59 | 7.5
Postmortem |  | 20 | 35 | 87 | 11
Total |  | 150 | 147 | 797 | 100.1
UPI (70%) |  | 239
LPI (70%) |  | 71
PSP3 Project Plan Summary - Program N/A (Continued)
Student | JAGB |  |  | Date | 2017-04-24
Program | Menú Reporte Maestros |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Defects Injected
Planning |  | 0 | 0 | 0 | 0
High-level Design |  | 0 | 0 | 0 | 0
HLDR |  | 0 | 0 | 0 | 0
Design |  | 1.3 | 0 | 5 | 12.2
Design Review |  | 0.5 | 0 | 2 | 4.9
Code |  | 8.1 | 3 | 34 | 82.9
Code Review |  | 0 | 0 | 0 | 0
Compile |  | 0 | 0 | 0 | 0
Test |  | 0 | 0 | 0 | 0
Total Development |  | 9.9 | 3 | 41 | 100
Defects Removed
Planning |  | 0 | 0 | 0 | 0
High-level Design |  | 0 | 0 | 0 | 0
HLDR |  | 0 | 0 | 0 | 0
Design |  | 0 | 0 | 0 | 0
Design Review |  | 1.8 | 0 | 7 | 17.1
Code |  | 0 | 0 | 0 | 0
Code Review |  | 6.3 | 3 | 27 | 65.9
Compile |  | 1.3 | 0 | 5 | 12.2
Test |  | 0.5 | 0 | 2 | 4.9
Total Development |  | 9.9 | 3 | 41 | 100.1
After Development |  |  | ????? | ?????
Defect Removal Efficiency
Def/Hr - HLDR |  | 0 | 0 | 0
Def/Hr - DLDR |  | 7.13 | 0 | 4.5
Def/Hr - CDR |  | 27.81 | 22.5 | 22.34
Def/Hr - Compile |  | 25.34 | 0 | 16.9
Def/Hr - Test |  | 2.85 | 0 | 2.02
DRL(HLDR/UT) |  | 0 | 0 | 0
DRL(DLDR/UT) |  | 2.5 | 0 | 2.23
DRL(CDR/UT) |  | 9.76 | 9.83 | 11.07
DRL(Compile/UT) |  | 8.89 | 0 | 8.37

## Size estimated template
Size Estimating Template
Student | JAGB |  |  |  | Date |  | 2017-04-24
Instructor | PEBM |  |  |  | Program# |  | N/A
BASE PROGRAM LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE SIZE (B) => |  |  |  |  | 30
LOC DELETED (D) => |  |  |  |  | 8
LOC MODIFIED (M) => |  |  |  |  | 10
OBJECT LOC
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC |  | C++ Object Size in LOC per Method
[9 empty] | Category | VS | S | M | L | VL
[9 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[9 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[9 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[9 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
(BA) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
TOTAL BASE ADDITIONS (BA) |  |  |  |  | 0 |  | 0 |  | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
Reporte_Maestros |  | VOID | I/O | L | 36 |  | 39
Main |  | VOID | I/O | VS | 9 |  | 6
(NO) subtotal from page 2 |  |  |  |  | 0 |  | 0
TOTAL NEW OBJECTS (NO) |  |  |  |  | 45 |  | 45
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
(R) subtotal from page 2 |  |  |  |  | 0 |  | 0
REUSED TOTAL (R) |  |  |  |  | 0 |  | 0
[5 empty] | Size |  | Time
Estimated Object LOC: |  |  | E = BA+NO+M |  | 55
Regression Parameter: |  |  | B0 |  | 0 |  | 0
Regression Parameter: |  |  | B1 |  | 1.2 |  | 2.26
Estimated New and Changed LOC: |  |  | N = B0 + B1` * E |  | 66
Estimated Total LOC: |  |  | T = N + B - D - M + R |  | 78
Estimated Total New Reuse (sum of * LOC): |  |  |  |  | 0
Estimated Total Developent Time: |  |  | Time = B0 + B1` * E |  |  |  | 81
Prediction Range: |  |  | Range |  | 0 |  | 0
Upper Prediction Interval: |  |  | UPI = N + Range |  | 0 |  | 0
Lower Prediction Interval: |  |  | LPI = N - Range |  | 0 |  | 0
Prediction Interval Percent |  |  |  |  | 70% |  | 70%
Method Selected |  |  |  |  | C |  | C
R^2 |  |  |  |  | 0 |  | 0
Size Estimating Template (continued)
Student | JAGB |  |  |  | Date |  | 2017-04-24
Instructor | PEBM |  |  |  | Program# |  | N/A
OBJECT LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC
C++ Object Size in LOC per Method
[15 empty] | Category | VS | S | M | L | VL
[15 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[15 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[15 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[15 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
[15 empty] | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
[15 empty] | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
SUBTOTAL BASE ADDITIONS (BA) => |  |  |  |  | 0 |  | 0
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
SUBTOTAL NEW OBJECTS (NO) => |  |  |  |  | 0 |  | 0
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
SUBTOTAL REUSED (R) => |  |  |  |  | 0 |  | 0

## Task Planning Template
| Project | Menú Reporte Maestros |  |  |  | Instructor | PEBM
Task |  | Plan |  |  |  |  | Actual
Number | Name | Minutes | Planned Value | Cumulative Minutes | Cumulative Planned Value | Date Monday | Date | Earned Value | Cumulative Earned Value
1 | Planning | 15 | 10% | 15 | 10% | 2017-04-24 | 2017-04-24 | 10% | 10%
2 | High-level Design | 5 | 3.333% | 20 | 13.33% | 2017-04-24 | 2017-04-24 | 3.333% | 13.33%
3 | HLDR | 5 | 3.333% | 25 | 16.67% | 2017-04-24 | 2017-04-24 | 3.333% | 16.67%
4 | Design | 35 | 23.33% | 60 | 40% | 2017-04-24 | 2017-04-24 | 23.33% | 40%
5 | Design Review | 20 | 13.33% | 80 | 53.33% | 2017-04-24 | 2017-04-24 | 13.33% | 53.33%
6 | Code | 20 | 13.33% | 100 | 66.67% | 2017-04-24 | 2017-04-26 | 13.33% | 66.67%
7 | Code Review | 10 | 6.667% | 110 | 73.33% | 2017-04-25 | 2017-04-26 | 6.667% | 73.33%
8 | Compile | 5 | 3.333% | 115 | 76.67% | 2017-04-25 | 2017-04-26 | 3.333% | 76.67%
9 | Test | 15 | 10% | 130 | 86.67% | 2017-04-25 | 2017-04-26 | 10% | 86.67%
10 | Postmortem | 20 | 13.33% | 150 | 100% | 2017-04-25 | 2017-04-27 | 13.33% | 100%
| Total | 150 | 100%

## Schedule Planning Template
Table C49 Schedule Planning Template
| Student | JAGB |  |  |  | Date | 2017-04-24
| Project | Menú Reporte Maestros |  |  |  | Instructor | PEBM
|  | Plan |  |  | Actual
Day Number | Date Monday | Direct Min | Cumutative Minute | Cumulative Planned Value | Direct Min | Cumulative Minutes | Cumulative Earned Value
4 | 2017-04-24 | 15 | 15 | 10% | 13 | 13 | 10%
4 | 2017-04-24 | 5 | 20 | 13.33% | 5 | 18 | 13.33%
4 | 2017-04-24 | 5 | 25 | 16.67% | 5 | 23 | 16.67%
4 | 2017-04-24 | 35 | 60 | 40% | 33 | 56 | 40%
4 | 2017-04-24 | 20 | 80 | 53.33% | 20 | 76 | 53.33%
7 | 2017-04-24 | 20 | 100 | 66.67% | 18 | 94 | 66.67%
7 | 26/04/17 | 10 | 110 | 73.33% | 8 | 102 | 73.33%
3 | 26/04/17 | 5 | 115 | 76.67% | 3 | 105 | 76.67%
3 | 26/04/17 | 15 | 130 | 86.67% | 7 | 112 | 86.67%
3 | 2017-04-27 | 20 | 150 | 100% | 35 | 147 | 100%