## Project Plan Summary
PSP3 Project Plan Summary
Student | RMM |  |  | Date | 2017-04-24
Program | Menú Reportes Materias |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Summary
LOC/Hour |  | 33.81 | 19.33 | 20.02
Planned Time |  | 82 |  | 1563
Actual Time |  |  | 90 | 1621
CPI (Planned/Actual Time) |  |  |  | 0.96
% Reused |  | 0 | 0 | 0
% New Reused |  | 0 | 0 | 32.2
Test Defects/KLOC |  | 6.6 | 0 | 6.02
Total Defects/KLOC |  | 66.01 | 0 | 60.24
Yield % |  | 90 | 100 | 90
% Appraisal COQ |  | 24 | 5.6 | 22.4
% Failure COQ |  | 13.9 | 5.6 | 13.1
COQ A/F Ratio |  | 1.73 | 1 | 1.7
Program Size (LOC)
Base(B) |  | 16 | 28
Deleted(D) |  | 2 | 4
Modified(M) |  | 5 | 0
Added(A) |  | 41 | 29
Reused(R) |  | 0 | 0 | 0
Total N&C (N) |  | 46 | 29 | 332
Total LOC(T) |  | 55 | 53 | 737
Total New Reused |  | 0 | 0 | 107
Total Object LOC(E) |  | 41.41 | 43 | 422
UPI (70%) |  | 68
LPI (70%) |  | 25
Time in Phase (min.)
Planning |  | 15 | 29 | 189 | 19
High-level Design |  | 0 | 13 | 13 | 1.3
HLDR |  | 0 | 3 | 3 | 0.3
Design |  | 18 | 20 | 221 | 22.2
Design Review |  | 8 | 0 | 83 | 8.3
Code |  | 15 | 9 | 174 | 17.5
Code Review |  | 12 | 5 | 140 | 14.1
Compile |  | 0 | 0 | 0 | 0
Test |  | 11 | 5 | 131 | 13.1
Postmortem |  | 3 | 6 | 42 | 4.2
Total |  | 82 | 90 | 995 | 100
UPI (70%) |  | 0
LPI (70%) |  | 0
Student | René Moratilla Montes |  |  | Date | 2017-04-24
Program | Menú Reportes Materias |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Defects Injected
Planning |  | 0 | 0 | 0 | 0
High-level Design |  | 0 | 0 | 0 | 0
HLDR |  | 0 | 0 | 0 | 0
Design |  | 1.7 | 0 | 11 | 55
Design Review |  | 0 | 0 | 0 | 0
Code |  | 1.4 | 0 | 9 | 45
Code Review |  | 0 | 0 | 0 | 0
Compile |  | 0 | 0 | 0 | 0
Test |  | 0 | 0 | 0 | 0
Total Development |  | 3.1 | 0 | 20 | 100
Defects Removed
Planning |  | 0 | 0 | 0 | 0
High-level Design |  | 0 | 0 | 0 | 0
HLDR |  | 0 | 0 | 0 | 0
Design |  | 0 | 0 | 0 | 0
Design Review |  | 1.5 | 0 | 10 | 50
Code |  | 0 | 0 | 0 | 0
Code Review |  | 1.2 | 0 | 8 | 40
Compile |  | 0 | 0 | 0 | 0
Test |  | 0.3 | 0 | 2 | 10
Total Development |  | 3.1 | 0 | 20 | 100
After Development |  |  | 0 | 0
Defect Removal Efficiency
Def/Hr - HLDR |  | 0 | 0 | 0
Def/Hr - DLDR |  | 12.24 | 0 | 7.27
Def/Hr - CDR |  | 5.98 | 0 | 3.43
Def/Hr - Compile |  | 0 | 0 | 0
Def/Hr - Test |  | 1.61 | 0 | 0.92
DRL(HLDR/UT) |  | 0 | 0 | 0
DRL(DLDR/UT) |  | 7.62 | 0 | 7.93
DRL(CDR/UT) |  | 3.73 | 0 | 3.74
DRL(Compile/UT) |  | 0 | 0 | 0

## Size estimated template
Size Estimating Template
Student | RMM |  |  |  | Date |  | 24/04/17.
Instructor | PEBM |  |  |  | Program# |  | Menú Reportes Materias
BASE PROGRAM LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE SIZE (B) => |  |  |  |  | 16 |  | 28
LOC DELETED (D) => |  |  |  |  | 2 |  | 4
LOC MODIFIED (M) => |  |  |  |  | 5 |  | 0
OBJECT LOC
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC |  | C++ Object Size in LOC per Method
[9 empty] | Category | VS | S | M | L | VL
[9 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[9 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[9 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[9 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
(BA) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
TOTAL BASE ADDITIONS (BA) |  |  |  |  | 0 |  | 0 |  | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
menu_reportes_materias() |  | text | 1 | L | 36.4 |  | 43
(NO) subtotal from page 2 |  |  |  |  | 0 |  | 0
TOTAL NEW OBJECTS (NO) |  |  |  |  | 36.4 |  | 43
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
(R) subtotal from page 2 |  |  |  |  | 0 |  | 0
REUSED TOTAL (R) |  |  |  |  | 0 |  | 0
[5 empty] | Size |  | Time
Estimated Object LOC: |  |  | E = BA+NO+M |  | 41.4
Regression Parameter: |  |  | B0 |  | 18.49 |  | 0
Regression Parameter: |  |  | B1 |  | 0.67 |  | 1.98
Estimated New and Changed LOC: |  |  | N = B0 + B1` * E |  | 46.3
Estimated Total LOC: |  |  | T = N + B - D - M + R |  | 55.3
Estimated Total New Reuse (sum of * LOC): |  |  |  |  | 0
Estimated Total Developent Time: |  |  | Time = B0 + B1` * E |  |  |  | 82.2
Prediction Range: |  |  | Range |  | 21.4 |  | 0
Upper Prediction Interval: |  |  | UPI = N + Range |  | 67.7
Lower Prediction Interval: |  |  | LPI = N - Range |  | 24.9
Prediction Interval Percent |  |  |  |  | 70% |  | 70%
Method Selected |  |  |  |  | A |  | C
R^2 |  |  |  |  | 0.88 |  | 0
Size Estimating Template (continued)
Student | RMM |  |  |  | Date |  | 24/04/17.
Instructor | PEBM |  |  |  | Program# |  | Menú Reportes Materias
OBJECT LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC
C++ Object Size in LOC per Method
[15 empty] | Category | VS | S | M | L | VL
[15 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[15 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[15 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[15 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
[15 empty] | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
[15 empty] | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
SUBTOTAL BASE ADDITIONS (BA) => |  |  |  |  | 0 |  | 0
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
SUBTOTAL NEW OBJECTS (NO) => |  |  |  |  | 0 |  | 0
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
SUBTOTAL REUSED (R) => |  |  |  |  | 0 |  | 0

## Task Planning Template
| Project | Menú Reportes Materias |  |  |  | Instructor | PEBM
Task |  | Plan |  |  |  |  | Actual
Number | Name | Minutes | Planned Value | Cumulative Minutes | Cumulative Planned Value | Date Monday | Date | Earned Value | Cumulative Earned Value
1 | Planning | 15 | 18.29% | 15 | 18.29% | 24/04/17 | 24/04/17 | 18.29% | 18.29%
2 | High-level Design | 0 | 0% | 15 | 18.29% | 24/04/17 | 24/04/17 | 0% | 18.29%
3 | HLDR | 0 | 0% | 15 | 18.29% | 24/04/17 | 24/04/17 | 0% | 18.29%
4 | Design | 18 | 21.95% | 33 | 40.24% | 25/04/17 | 25/04/17 | 21.95% | 40.24%
5 | Design Review | 8 | 9.756% | 41 | 50% | 25/04/17 | 25/04/17 | 9.756% | 50%
6 | Code | 15 | 18.29% | 56 | 68.29% | 25/04/17 | 25/04/17 | 18.29% | 68.29%
7 | Code Review | 12 | 14.63% | 68 | 82.93% | 25/04/17 | 25/04/17 | 14.63% | 82.93%
8 | Compile | 0 | 0% | 68 | 82.93% | 26/04/17 | 25/04/17 | 0% | 82.93%
9 | Test | 11 | 13.41% | 79 | 96.34% | 26/04/17 | 25/04/17 | 13.41% | 96.34%
10 | Postmortem | 3 | 3.659% | 82 | 100% | 26/04/17 | 25/04/17 | 3.659% | 100%
| Total | 82 | 100% |  |  |  |  | 100%

## Schedule Planning Template
Table C49 Schedule Planning Template
| Student | RMM |  |  |  | Date | 24/04/17
| Project | Menú Reportes Materias |  |  |  | Instructor | PEBM
|  | Plan |  |  | Actual
Day Number | Date Monday | Direct Min | Cumutative Minute | Cumulative Planned Value | Direct Min | Cumulative Minutes | Cumulative Earned Value | Adjusted Earned Value
1 | 24/04/17 | 15 | 15 | 18.29% | 72 | 72 | 64.86% | 64.86%
2 | 25/04/17 | 53 | 68 | 64.63% | 39 | 111 | 35.14% | 100%
3 | 26/04/17 | 14 | 82 | 17.07%