## Summary
PSP2.1 Project Plan Summary - Program Menú Reportes Planes
Student | GVV |  |  | Date | 21/04/17
Program | Menú Rep.Planes |  |  | Program# | ########
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Summary
LOC/Hour |  | 24.12 | 8.76 | 29.45
Planned Time |  | 76 |  | 913
Actual Time |  |  | 116 | 1083
CPI (Planned/Actual Time) |  |  |  | 0.84
% Reused |  | 0 | 0 | 0
% New Reused |  | 0 | 0 | 0
Test Defects/KLOC |  | 0 | 0 | 0
Total Defects/KLOC |  | 45.71 | 1470.59 | 171.88
Yield % |  | 87.5 | 84 | 84.8
% Appraisal COQ |  | 12.1 | 6.7 | 10.5
% Failure COQ |  | 7.8 | 4.7 | 6.9
COQ A/F Ratio |  | 1.55 | 1.44 | 1.53
Program Size (LOC)
Base(B) |  | 15 | 50
Deleted(D) |  | 7 | 10
Modified(M) |  | 5 | 8
Added(A) |  | 26 | 9
Reused(R) |  | 0 | 0 | 0
Total N&C (N) |  | 31 | 17 | 192
Total LOC(T) |  | 34 | 49 | 436
Total New Reused |  | 0 | 0 | 0
Total Object LOC(E) |  | 28.7 | 14 | 187
UPI (70%)
LPI (70%)
Time in Phase (min.)
Planning |  | 22 | 22 | 101 | 25.9
Design |  | 16 | 60 | 118 | 30.1
Design Review |  | 4 | 7 | 20 | 5.1
Code |  | 20 | 8 | 79 | 20.2
Code Review |  | 6 | 1 | 21 | 5.4
Compile |  | 0 | 0 | 2 | 0.4
Test |  | 5 | 5 | 25 | 6.4
Postmortem |  | 3 | 14 | 25 | 6.4
Total |  | 76 | 116 | 391 | 100
UPI (70%) |  | 103
LPI (70%) |  | 50
PSP2.1 Project Plan Summary - Program Menú Reportes Planes
Student | GVV |  |  | Date | 21/04/17
Program | Menú Rep.Planes |  |  | Program# | ########
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Defects Injected
Planning |  | 0 | 4 | 4 | 12.1
Design |  | 0.2 | 20 | 21 | 63.6
Design Review |  | 0 | 0 | 0 | 0
Code |  | 1.2 | 1 | 8 | 24.2
Code Review |  | 0 | 0 | 0 | 0
Compile |  | 0 | 0 | 0 | 0
Test |  | 0 | 0 | 0 | 0
Total Development |  | 1.4 | 25 | 33 | 100
Defects Removed
Planning |  | 0 | 0 | 0 | 0
Design |  | 0 | 0 | 0 | 0
Design Review |  | 0.2 | 20 | 21 | 63.6
Code |  | 0 | 0 | 0 | 0
Code Review |  | 1.1 | 1 | 7 | 21.2
Compile |  | 0.2 | 4 | 5 | 15.2
Test |  | 0 | 0 | 0 | 0
Total Development |  | 1.4 | 25 | 33 | 100
After Development |  |  | 0 | 0
Defect Removal Efficiency
Def/Hr - DLDR |  | 2.86 | 179.1 | 63.16
Def/Hr - CDR |  | 11.34 | 55.38 | 19.87
Def/Hr - Compile |  | 22.28 | 4800 | 171.43
Def/Hr - Test |  | 0 | 0 | 0
DRL(DLDR/UT) |  | 0 | 0 | 0
DRL(CDR/UT) |  | 0 | 0 | 0
DRL(Compile/UT) |  | 0 | 0 | 0

## Size Estimating Template
Size Estimating Template
Student | GVV |  |  |  | Date |  | 21/04/2017
Instructor | PEBM |  |  |  | Program# |  | ######
BASE PROGRAM LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE SIZE (B) => |  |  |  |  | 15 |  | 50
LOC DELETED (D) => |  |  |  |  | 7 |  | 10
LOC MODIFIED (M) => |  |  |  |  | 5 |  | 8
OBJECT LOC
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC
menu_planes() |  | I/O | 1 | M | 16.2 |  | 1 |  | C++ Object Size in LOC per Method
[9 empty] | Category | VS | S | M | L | VL
[9 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[9 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[9 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
(BA) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
TOTAL BASE ADDITIONS (BA) |  |  |  |  | 16.2 |  | 1 |  | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | * | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
int_main |  | Logic | 1 | VS | 7.6 |  | 5
(NO) subtotal from page 2 |  |  |  |  | 0 |  | 0
TOTAL NEW OBJECTS (NO) |  |  |  |  | 7.6 |  | 5
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
(R) subtotal from page 2 |  |  |  |  | 0 |  | 0
REUSED TOTAL (R) |  |  |  |  | 0 |  | 0
[5 empty] | Size |  | Time
Estimated Object LOC: |  |  | E = BA+NO+M |  | 28.7
Regression Parameter: |  |  | B0 |  | 0 |  | 51.51
Regression Parameter: |  |  | B1 |  | 1.07 |  | 0.86
Estimated New and Changed LOC: |  |  | N = B0 + B1` * E |  | 30.6
Estimated Total LOC: |  |  | T = N + B - D - M + R |  | 33.6
Estimated Total New Reuse (sum of * LOC): |  |  |  |  | 0
Estimated Total Developent Time: |  |  | Time = B0 + B1` * E |  |  |  | 76.2
Prediction Range: |  |  | Range |  | 0 |  | 26.6
Upper Prediction Interval: |  |  | UPI = N + Range |  |  |  | 102.8
Lower Prediction Interval: |  |  | LPI = N - Range |  |  |  | 49.6
Prediction Interval Percent |  |  |  |  | 70% |  | 70%
Method Selected |  |  |  |  | C |  | B
R^2 |  |  |  |  | 0 |  | 0.75
Size Estimating Template (continued)
Student | Guillermo Vivaldo Vazquez |  |  |  | Date |  | ?????
Instructor | Jorge Rafael Aguilar Cisneros |  |  |  | Program# |  | #######
OBJECT LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC
C++ Object Size in LOC per Method
[9 empty] | Category | VS | S | M | L | VL
[9 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[9 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[9 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[9 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
[9 empty] | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
[9 empty] | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
*
SUBTOTAL NEW OBJECTS (NO) => |  |  |  |  | 0 |  | 101
SUBTOTAL NEW OBJECTS (NO) => |  |  |  |  | 0 |  | 0
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
SUBTOTAL REUSED (R) => |  |  |  |  | 0 |  | 0

## TaskPlanning
| Project | Menú-Reporte-Planes |  |  |  | Instructor | PEBM
Task |  | Plan |  |  |  |  | Actual
Number | Name | Minutes | Planned Value | Cumulative Minutes | Cumulative Planned Value | Date Monday | Date | Earned Value | Cumulative Earned Value
1 | Planning | 22 | 20% | 22 | 20% | 2017-04-21 | 2017-04-21 | 20% | 20%
2 | High-level Design | 0 | 0% | 22 | 20% | 2017-04-21 | 2017-04-21 | 0% | 20%
3 | HLDR | 0 | 0% | 22 | 20% | 2017-04-21 | 2017-04-21 | 0% | 20%
4 | Design | 16 | 46% | 38 | 66% | 2017-04-22 | 2017-04-23 | 46% | 66%
5 | Design Review | 4 | 6% | 42 | 72% | 2017-04-22 | 2017-04-23 | 6% | 72%
6 | Code | 20 | 14% | 62 | 86% | 2017-04-22 | 2017-04-25 | 14% | 86%
7 | Code Review | 6 | 6% | 68 | 92% | 2017-04-22 | 2017-04-25 | 6% | 92%
8 | Compile | 0 | 1% | 68 | 93% | 2017-04-22 | 2017-04-25 | 1% | 93%
9 | Test | 5 | 5% | 73 | 98% | 2017-04-22 | 2017-04-26 | 5% | 98%
10 | Postmortem | 3 | 2% | 76 | 100% | 2017-04-22 | 2017-04-26 | 2% | 100%
| Total | 76 | 100%
Formulas:
PEBM = [Instructor]

## SchedulePlanning
Table C49 Schedule Planning Template
| Student | GVV |  |  |  | Date | 21/04/17
| Project | Menú Reporte Planes |  |  |  | Instructor | PEBM
|  | Plan |  |  | Actual
Day Number | Date Monday | Direct Min | Cumutative Minute | Cumulative Planned Value | Direct Min | Cumulative Minutes | Cumulative Earned Value | Adjusted Earned Value
1 | 2017-04-21 | 22 | 22 | 20% | 21.6 | 21.6 | 20% | 18.54%
2 | 2017-04-22 | 54 | 76 | 100% | 0 | 21.6 | 20% | 18.54%
3 | 2017-04-23 |  |  |  | 67 | 88.6 | 66% | 76.05%
4 | 2017-04-24 |  |  |  | 0 | 88.6 | 66% | 76.05%
5 | 2017-04-25 |  |  |  | 9 | 97.6 | 93% | 83.78%
6 | 2017-04-26 |  |  |  | 18.9 | 116.5 | 100% | 100%