## Project Plan Summary
PSP3 Project Plan Summary
Student | BRA |  |  | Date | 2017-04-26
Program | Menú Reportes |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Summary
LOC/Hour |  | 38.81
Planned Time |  | 107
Actual Time
CPI (Planned/Actual Time)
% Reused |  | 0
% New Reused |  | 0
Test Defects/KLOC |  | 2.92
Total Defects/KLOC |  | 26.24
Yield % |  | 88.9
% Appraisal COQ |  | 7.2
% Failure COQ |  | 5.7
COQ A/F Ratio |  | 1.28
Program Size (LOC)
Base(B) |  | 0 | 0
Deleted(D) |  | 0 | 0
Modified(M) |  | 0 | 0
Added(A) |  | 69 | 46
Reused(R) |  | 0 | 0
Total N&C (N) |  | 69 | 46
Total LOC(T) |  | 69 | 46
Total New Reused |  | 0 | 0
Total Object LOC(E) |  | 30.63 | 46
UPI (70%) |  | 120
LPI (70%) |  | 18
Time in Phase (min.)
Planning |  | 21 | 25 | 61 | 22.02%
High-level Design |  | 20 | 4 | 38 | 13.72%
HLDR |  | 7 | 3 | 16 | 5.776%
Design |  | 25 | 20 | 64 | 23.1%
Design Review |  | 6 | 2 | 12 | 4.332%
Code |  | 14 | 6 | 30 | 10.83%
Code Review |  | 4 | 2 | 9 | 3.249%
Compile |  | 0 | 0 | 0 | 0%
Test |  | 1 | 9 | 10 | 3.61%
Postmortem |  | 9 | 21 | 37 | 13.36%
Total |  | 107 | 92 | 277 | 100%
UPI (70%) |  | 166
LPI (70%) |  | 25
PSP3 Project Plan Summary - Program (Continued)
Student | BRA |  |  | Date | 2017-04-26
Program | Menú maestros |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Defects Injected
Planning |  | 0.6
High-level Design |  | 0
HLDR |  | 0
Design |  | 0.2
Design Review |  | 0
Code |  | 1
Code Review |  | 0
Compile |  | 0
Test |  | 0
Total Development |  | 1.8
Defects Removed
Planning |  | 0.4
High-level Design |  | 0
HLDR |  | 0
Design |  | 0.2
Design Review |  | 0.2
Code |  | 0
Code Review |  | 0.8
Compile |  | 0
Test |  | 0.2
Total Development |  | 1.8
After Development
Defect Removal Efficiency
Def/Hr - HLDR |  | 0
Def/Hr - DLDR |  | 3.26
Def/Hr - CDR |  | 12.07
Def/Hr - Compile |  | 0
Def/Hr - Test |  | 2.16
DRL(HLDR/UT) |  | 0
DRL(DLDR/UT) |  | 1.51
DRL(CDR/UT) |  | 5.58
DRL(Compile/UT) |  | 0

## Size estimated template
Size Estimating Template
Student | BRA |  |  |  | Date |  | 2017-04-26
Instructor | PEBM |  |  |  | Program# |  | Menú Reportes
BASE PROGRAM LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE SIZE (B) => |  |  |  |  | 0 |  | 0
LOC DELETED (D) => |  |  |  |  | 0 |  | 0
LOC MODIFIED (M) => |  |  |  |  | 0 |  | 0
OBJECT LOC
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC |  | C++ Object Size in LOC per Method
[9 empty] | Category | VS | S | M | L | VL
[9 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[9 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[9 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[9 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
(BA) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
TOTAL BASE ADDITIONS (BA) |  |  |  |  | 0 |  | 0 |  | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
Menu_reportes() |  | I/O | 1 | L | 21.62 |  | 37
int main() |  | I/O | 1 | VS | 9.01 |  | 9
(NO) subtotal from page 2 |  |  |  |  | 0 |  | 0
TOTAL NEW OBJECTS (NO) |  |  |  |  | 30.63 |  | 46
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
(R) subtotal from page 2 |  |  |  |  | 0 |  | 0
REUSED TOTAL (R) |  |  |  |  | 0 |  | 0
[5 empty] | Size |  | Time
Estimated Object LOC: |  |  | E = BA+NO+M |  | 30.63
Regression Parameter: |  |  | B0 |  | 0 |  | 0
Regression Parameter: |  |  | B1 |  | 1.2 |  | 2.26
Estimated New and Changed LOC: |  |  | N = B0 + B1` * E |  | 36.756
Estimated Total LOC: |  |  | T = N + B - D - M + R |  | 36.756
Estimated Total New Reuse (sum of * LOC): |  |  |  |  | 0
Estimated Total Developent Time: |  |  | Time = B0 + B1` * E |  |  |  | 81
Prediction Range: |  |  | Range |  | 0 |  | 0
Upper Prediction Interval: |  |  | UPI = N + Range |  | 0 |  | 0
Lower Prediction Interval: |  |  | LPI = N - Range |  | 0 |  | 0
Prediction Interval Percent |  |  |  |  | 70% |  | 70%
Method Selected |  |  |  |  | C |  | C
R^2 |  |  |  |  | 0 |  | 0
Size Estimating Template (continued)
Student | BRA |  |  |  | Date |  | 2017-04-26
Instructor | PEBM |  |  |  | Program# |  | Menú Reportes
OBJECT LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC
C++ Object Size in LOC per Method
[15 empty] | Category | VS | S | M | L | VL
[15 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[15 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[15 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[15 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
[15 empty] | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
[15 empty] | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
SUBTOTAL BASE ADDITIONS (BA) => |  |  |  |  | 0 |  | 0
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
SUBTOTAL NEW OBJECTS (NO) => |  |  |  |  | 0 |  | 0
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
SUBTOTAL REUSED (R) => |  |  |  |  | 0 |  | 0

## Task Planning Template
| Project | Menú Reportes |  |  |  | Instructor | PEBM
Task |  | Plan |  |  |  |  | Actual
Number | Name | Minutes | Planned Value | Cumulative Minutes | Cumulative Planned Value | Date Monday | Date | Earned Value | Cumulative Earned Value
1 | Planning | 21 | 19.63% | 21 | 19.63% | 2017-04-22 | 2017-04-26 | 19.63% | 19.63%
2 | High-level Design | 20 | 18.69% | 41 | 38.32% | 2017-04-25 |  | 38.32% | 57.94%
3 | HLDR | 7 | 6.542% | 48 | 44.86% | 2017-04-25 |  | 44.86% | 102.8%
4 | Design | 25 | 23.36% | 73 | 68.22% | 2017-04-25 |  | 68.22% | 171%
5 | Design Review | 6 | 5.607% | 79 | 73.83% | 2017-04-25 |  | 73.83% | 244.9%
6 | Code | 14 | 13.08% | 93 | 86.92% | 2017-04-26 |  | 86.92% | 331.8%
7 | Code Review | 4 | 3.738% | 97 | 90.65% | 2017-04-26 |  | 90.65% | 422.4%
8 | Compile | 0 | 0% | 97 | 90.65% | 2017-04-26 |  | 90.65% | 513.1%
9 | Test | 1 | 0.9346% | 98 | 91.59% | 2017-04-27 |  | 91.59% | 604.7%
10 | Postmortem | 9 | 8.411% | 107 | 100% | 2017-04-27 |  | 100% | 704.7%
| Total | 107 | 100%

## Schedule Planning Template
Table C49 Schedule Planning Template
| Student | BRA |  |  |  | Date | 2017-04-26
| Project | Menú Reportes |  |  |  | Instructor | PEBM
|  | Plan |  |  | Actual
Day Number | Date Monday | Direct Min | Cumutative Minute | Cumulative Planned Value | Direct Min | Cumulative Minutes | Cumulative Earned Value | Adjusted Earned Value
1 | 2017-04-22 | 21 | 21 | 19.63%
2 | 2017-04-25 | 58 | 79 | 73.83%
3 | 2017-04-26 | 18 | 97 | 90.65%
4 | 2017-04-27 | 10 | 107 | 100%