## Project Plan Summary
PSP3 Project Plan Summary - Transformación DB
Student | BRA |  |  | Date | 2017-04-26
Program | Transformación DB |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Summary
LOC/Hour |  | 51.65 | -53.01
Planned Time |  | 68
Actual Time
CPI (Planned/Actual Time)
% Reused |  | 0
% New Reused |  | 0
Test Defects/KLOC |  | 2.92
Total Defects/KLOC |  | 26.24
Yield % |  | 88.9
% Appraisal COQ |  | 7.2
% Failure COQ |  | 5.7
COQ A/F Ratio |  | 1.28
Program Size (LOC)
Base(B) |  | 107 | 107
Deleted(D) |  | 8 | 62
Modified(M) |  | 0 | 14
Added(A) |  | 59 | 82
Reused(R) |  | 112 | 117
Total N&C (N) |  | 59 | 96
Total LOC(T) |  | 270 | 244
Total New Reused |  | 0 | 0
Total Object LOC(E) |  | 0 | 14
UPI (70%) |  | 118
LPI (70%) |  | 0
Time in Phase (min.)
Planning |  | 13
High-level Design |  | 12
HLDR |  | 5
Design |  | 16
Design Review |  | 4
Code |  | 9
Code Review |  | 3
Compile |  | 0
Test |  | 0
Postmortem |  | 6
Total |  | 68
UPI (70%) |  | 146
LPI (70%) |  | 0
PSP3 Project Plan Summary - Program (Continued)
Student | BRA |  |  | Date | 2017-04-26
Program | Transformación DB |  |  | Program# | N/A
Instructor | PEBM |  |  | Language | C
|  | Plan | Actual | To Date | To Date%
Defects Injected
Planning |  | 0.5
High-level Design |  | 0
HLDR |  | 0
Design |  | 0.2
Design Review |  | 0
Code |  | 0.9
Code Review |  | 0
Compile |  | 0
Test |  | 0
Total Development |  | 1.5
Defects Removed
Planning |  | 0.3
High-level Design |  | 0
HLDR |  | 0
Design |  | 0.2
Design Review |  | 0.2
Code |  | 0
Code Review |  | 0.7
Compile |  | 0
Test |  | 0.2
Total Development |  | 1.5
After Development
Defect Removal Efficiency
Def/Hr - HLDR |  | 0
Def/Hr - DLDR |  | 4.33
Def/Hr - CDR |  | 16.06
Def/Hr - Compile |  | 0
Def/Hr - Test |  | 2.88
DRL(HLDR/UT) |  | 0
DRL(DLDR/UT) |  | 1.51
DRL(CDR/UT) |  | 5.58
DRL(Compile/UT) |  | 0

## Size estimated template
Size Estimating Template
Student | BRA |  |  |  | Date |  | 2017-04-26
Instructor | PEBM |  |  |  | Program# |  | Transformación DB
BASE PROGRAM LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE SIZE (B) => |  |  |  |  | 107 |  | 107
LOC DELETED (D) => |  |  |  |  | 8 |  | 62
LOC MODIFIED (M) => |  |  |  |  | 0 |  | 14
OBJECT LOC
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC |  | C++ Object Size in LOC per Method
[9 empty] | Category | VS | S | M | L | VL
[9 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[9 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[9 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[9 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
(BA) subtotal from page 2 |  |  |  |  | 0 |  | 0 |  | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
TOTAL BASE ADDITIONS (BA) |  |  |  |  | 0 |  | 0 |  | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
(NO) subtotal from page 2 |  |  |  |  | 0 |  | 0
TOTAL NEW OBJECTS (NO) |  |  |  |  | 0 |  | 0
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
Query |  |  |  |  | 112 |  | 117
(R) subtotal from page 2 |  |  |  |  | 0 |  | 0
REUSED TOTAL (R) |  |  |  |  | 112 |  | 117
[5 empty] | Size |  | Time
Estimated Object LOC: |  |  | E = BA+NO+M |  | 0
Regression Parameter: |  |  | B0 |  | 0 |  | 0
Regression Parameter: |  |  | B1 |  | 1.2 |  | 2.26
Estimated New and Changed LOC: |  |  | N = B0 + B1` * E |  | 0
Estimated Total LOC: |  |  | T = N + B - D - M + R |  | 211
Estimated Total New Reuse (sum of * LOC): |  |  |  |  | 0
Estimated Total Developent Time: |  |  | Time = B0 + B1` * E |  |  |  | 81
Prediction Range: |  |  | Range |  | 0 |  | 0
Upper Prediction Interval: |  |  | UPI = N + Range |  | 0 |  | 0
Lower Prediction Interval: |  |  | LPI = N - Range |  | 0 |  | 0
Prediction Interval Percent |  |  |  |  | 70% |  | 70%
Method Selected |  |  |  |  | C |  | C
R^2 |  |  |  |  | 0 |  | 0
Size Estimating Template (continued)
Student | BRA |  |  |  | Date |  | 2017-04-26
Instructor | PEBM |  |  |  | Program# |  | Transformación DB
OBJECT LOC |  |  |  |  | ESTIMATE |  | ACTUAL
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | LOC |  | LOC
C++ Object Size in LOC per Method
[15 empty] | Category | VS | S | M | L | VL
[15 empty] | Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
[15 empty] | Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
[15 empty] | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
[15 empty] | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
[15 empty] | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
[15 empty] | Text | 3.75 | 8 | 17.07 | 36.41 | 77.66
SUBTOTAL BASE ADDITIONS (BA) => |  |  |  |  | 0 |  | 0
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | LOC | * | LOC | *
SUBTOTAL NEW OBJECTS (NO) => |  |  |  |  | 0 |  | 0
REUSED OBJECTS |  |  |  |  | LOC |  | LOC
SUBTOTAL REUSED (R) => |  |  |  |  | 0 |  | 0

## Task Planning Template
| Project | Transformación DB |  |  |  | Instructor | PEBM
Task |  | Plan |  |  |  |  | Actual
Number | Name | Minutes | Planned Value | Cumulative Minutes | Cumulative Planned Value | Date Monday | Date | Earned Value | Cumulative Earned Value
1 | Planning | 13 | 19.12% | 13 | 19.12% | 2017-04-26 | 2017-04-26 | 19.12% | 19.12%
2 | High-level Design | 12 | 17.65% | 25 | 36.76% | 2017-04-26 |  | 36.76% | 55.88%
3 | HLDR | 5 | 7.353% | 30 | 44.12% | 2017-04-26 |  | 44.12% | 100%
4 | Design | 16 | 23.53% | 46 | 67.65% | 2017-04-26 |  | 67.65% | 167.6%
5 | Design Review | 4 | 5.882% | 50 | 73.53% | 2017-04-26 |  | 73.53% | 241.2%
6 | Code | 9 | 13.24% | 59 | 86.76% | 2017-04-26 |  | 86.76% | 327.9%
7 | Code Review | 3 | 4.412% | 62 | 91.18% | 2017-04-26 |  | 91.18% | 419.1%
8 | Compile | 0 | 0% | 62 | 91.18% | 2017-04-27 |  | 91.18% | 510.3%
9 | Test | 0 | 0% | 62 | 91.18% | 2017-04-27 |  | 91.18% | 601.5%
10 | Postmortem | 6 | 8.824% | 68 | 100% | 2017-04-27 |  | 100% | 701.5%
| Total | 68 | 100%

## Schedule Planning Template
Table C49 Schedule Planning Template
| Student | BRA |  |  |  | Date | 2017-04-26
| Project | Transformación DB |  |  |  | Instructor | PEBM
|  | Plan |  |  | Actual
Day Number | Date Monday | Direct Min | Cumutative Minute | Cumulative Planned Value | Direct Min | Cumulative Minutes | Cumulative Earned Value | Adjusted Earned Value
1 | 2017-04-26 | 46 | 46 | 67.65% |  |  | 67.65% | #DIV/0!
2 | 2017-04-26 | 22 | 68 | 100% |  | 0 | 100% | #DIV/0!